SEN381 - CIVICCONNECT PROJECT

Project Engineering Document (PED)

Milestone 3 – Controlled construction, Integration and Quality & Release readiness

Version 3.0

Team Name / Number: Proto

Team Members:

Jared Swanepoel - 601621

Michael Cheyne - 602441

Xander Oosthuyzen - 601256

Module: Software Engineering 381 (SEN381)

Governing document: SEN381 CivicConnect Master Project Brief

Submission Date: 16/10/2026

Table of Contents

Document Control	6

Change record	8

Baseline Approval	12

Baseline Approval (Milestone 2)	12

1. Problem Statement & Business Need	14

1.1 Problem Statement	14

1.2 Business Need	14

1.3 Intended Business Value	14

2. Stakeholder Analysis	14

3. Scope Baseline	15

3.1 In Scope	15

3.2 Out of Scope	16

3.3 Deferred / Future Scope	16

3.4 Defended Exclusion / Deferment	16

3.5 Scope baseline reviews and changes	16

4. Requirements & Acceptance Criteria	17

4.1 Functional Requirements	17

4.2 Non-Functional Requirements	19

4.3 Architecturally Significant Requirements and Quality Drivers	21

5. Constraints	23

5.1 Constraint Interaction / Trade-off	24

5.2 Assumptions and Dependencies	25

6. Requirements Traceability Matrix (RTM)	26

6.1 Matrix filled by Milestone 1	26

6.2 Matrix filled by Milestone 2	29

6.3 Matrix filled by Milestone 3	34

7. Risk Register	38

7.1 Index	38

8. Forward Engineering Considerations	53

9. Engineering Decision Log	55

9.1 Index	55

10. GitHub & Team Governance	71

10.1 Repository	71

10.2 Team Working Agreement	72

10.3 Repository structure and continuous integration	72

11. AI Usage Register	73

12. Baseline Readiness Checklist	76

Milestone 1 Readiness Checklist	76

Milestone 2 Readiness Checklist	76

13. Solution Design Baseline	77

13.1 Architecture	77

13.1.1 Logical components	77

13.1.2 Considered alternatives	78

13.1.3 Justification of selected architecture	79

13.1.4 Physical deployment	79

13.1.5 Architectural diagrams	80

13.2 Data and persistence baseline	81

Intro	81

13.2.1 Core data entities	81

13.2.2 ERD	82

13.2.3 Data Ownership and Lifecycle	83

13.2.4 Persistence model choice	84

13.2.5 SPOF, scalability and bottlenecks	85

13.2.6 Milestone 3 Update: schema prototype and verification.	85

13.3 Tech Stack Analysis	85

13.3.1 Common web bundles	85

13.3.2 Candidates not recommended	86

13.3.3 Weight matrix	86

13.3.4 Weight matrix for database	87

13.3.5 Results of the matrices	88

13.3.6 Selected versions and compatibility	88

13.4 Design Decisions	89

13.4.1 Design Problem 1: Status-Change Side Effects	90

Problem	90

Assignment 2 Alternatives	90

Final Decision (adapts the Assignment 2 recommendation)	90

Trade-off	90

Class / Flow Diagram	90

Planned implementation (Milestone 3)	91

13.4.2 Design Problem 2: Category-Specific Request Handling	92

Problem	92

Assignment 2 Alternatives	92

Final Decision	92

Trade-off	92

Class Diagram	92

Planned implementation (Milestone 3)	93

13.5 UI & Information Architecture	94

13.5.1 Role Sitemap	94

13.5.2 Wireframes	94

13.5.3 Usability and Accessibility Rationale	95

13.6 Interfaces and Integration	97

13.6.1 Interface inventory	97

13.6.2 Page contracts	97

13.6.3 Failure behaviour	99

13.6.4 Internal event contract	99

13.6.5 External interface: mail provider	99

13.6.6 Change and versioning	100

13.6.7 Interactions not yet established	100

13.7 Deployment & Environments	100

13.7.1 Environment Structure	100

13.7.2 Configuration and Secrets	101

13.7.3 Queue worker and scheduler	101

13.7.4 Free-Tier Limits	101

13.7.5 Backup and Recovery	101

13.8 Open and Deferred Decisions	102

References	104

# Submission Information

| Item | Information |
| --- | --- |
| Team | Proto: Jared Swanepoel (601621), Michael Cheyne (602441), Xander Oosthuyzen (601256) |
| Repository | https://github.com/Destroyer1819/SEN381_Project |
| Release candidate | v3.0-rc1 (main, commit abc1234) |
| PED version | v3.0 |
| RTM | PED Section 6 (6.3 for Milestone 3) |
| CI evidence | GitHub Actions, workflow "Tests": https://github.com/Destroyer1819/SEN381_Project/actions/workflows/tests.yml (latest passing run: https://github.com/Destroyer1819/SEN381_Project/actions/runs/38868569090 |
| Staging | https://civicconnect-staging-kski.onrender.com (Render free tier, Neon staging branch; verified 16/10/2026: login, status change with email to the demo inbox, dashboard) |

# Document Control

| Version | Date | Author(s) | Summary of Change | Reviewed By |
| --- | --- | --- | --- | --- |
| 0.1 | 07/09/2026 | Xander | Initial Template | Michael, Jared |
| 0.2 | 07/09/2026 | Xander | Sections 5, 7, 8, 9, 10 filled out | Michael |
| 0.3 | 09/09/2026 | Michael | Sections 4, 6 added |  |
| 0.4 | 09/09/2026 | Xander (AI-assisted) | AI Usage Register entries added for Sections 5/7/8/9/10 AI assistance; Risk Register owners assigned; Team Working Agreement drafted; FR-001 wording aligned between Section 4 and the RTM | Michael |
| 0.5 | 09/09/2026 | Jared | Sections 1, 2, 3 added to the main assignment | Michael |
| 1.0 | 09/09/2026 | Michael, Jared, Xander | Initial PED version 1.0 for Milestone 1 signed off | Michael, Jared, Xander |
| 1.2 | 22/09/2026 | Michael | Spelling corrections. Section 2: lecturer added as stakeholder. Section 3: expanded the WhatsApp exclusion, added the reasoning for excluding multi-language support and for the 5-year retention. Section 5: rationale now cited. Section 6: restored a missing functional requirement | Jared, Xander |
| 1.3 | 23/09/2026 | Michael | Section 4: added 4.3 Architecturally Significant Requirements; Section 5: added constraint IDs and CON-007 technology environment; Section 6: split the RTM into 6.1 (M1) and 6.2 (M2) | Jared, Xander |
| 1.4 | 24/09/2026 | Jared | Section 2: added the ASR influence column; Section 3: scope reviewed for v2.0; change record started | Michael, Xander |
| 1.5 | 25/09/2026 | Michael | Section 13.1 architecture and 13.2 data and persistence baseline drafted | Jared, Xander |
| 1.6 | 25/09/2026 | Xander | Sections 13.4 design decisions, 13.5 UI and information architecture, 13.7 deployment and environments drafted | Michael, Jared |
| 1.7 | 26/09/2026 | Jared | Section 13.3 technology stack analysis and weighted matrices added | Michael, Xander |
| 1.8 | 26/09/2026 | Xander | Section 7 risk register restructured per risk, R-008 to R-016 added; Section 8 Milestone 2 status added and FEC 7 and 8 raised; Section 9 decision log restructured per decision, D-006 to D-015 added; Section 10 governance updated | Michael, Jared |
| 1.9 | 26/09/2026 | Jared | Change record completed (CR-001 to CR-016); Section 11 AI Usage Register updated for Milestone 2; Section 12 Milestone 2 readiness checklist added; References extended | Michael, Xander |
| 1.9.1 | 27/09/2026 | Jared | Team member names corrected; bundle ID B-002 corrected; checklist symbols removed; Section 10.3 repository structure added; NFR-009 and ASR-004 review wording changed; D-001 category list changed; 13.2.1 requirement links updated | Michael, Xander |
| 1.10 | 27/09/2026 | Jared | Consistency review applied: CR-017 recorded and SPA wording replaced in 13.1, 13.5 and 13.7; CR-009, CR-012 and CR-013 applied; CR-018 and CR-019 raised; NFR-009, ASR-004 and D-001 restored to the baseline wording; 13.2.4 completed; 5.2 assumptions and 13.3.6 versions added; references corrected | Michael, Xander |
| 1.11 | 27/09/2026 | Jared | Consistency review applied (part 2): 13.5 and 13.6 updated for Inertia; all six figures redrawn (Figures 13.1 to 13.6); Section 13 heading restored; references corrected in Source Manager | Michael, Xander |
| 2.0 | 30/09/2026 | Jared | Grammer fixes such as section 13.7.2 was missing a full stop; Change document name to SEN381 Proto PED Milestone 2 V2.0 | Michael, Xander |
| 2.2 | 12/10/2026 | Michael | Added sections 6.3 and 13.2.6 which is filled by Milestone 3’s work. Updated the AI register. Updated 13.7.4 and 13.7.5. recorded the database provider for OD-01. |  |
| 2.3 | 15/10/2026 | Michael | Added the decisions of the Emailing service, database hosting site and application hosting site. Updated all section impacted by this. |  |
| 3 | 16/10/2026 | Michael, Jared, Xander | Milestone 3 version. Added the submission information block, Section 14 (construction, quality and release readiness), Section 15 Technical Debt Register and Section 16 Defect Register. Added the Milestone 3 status column to 13.8 and the M3 rows to RTM 6.3. Added D-020 (offer and decline rule) and the Render deployment evidence to D-018; corrected the D-019 heading. Document renamed to SEN381 Proto PED Milestone 3 V3.0. |  |

## Change record

| CR | Date | Raised by | Item | Change | Reason | Impact | Decision |
| --- | --- | --- | --- | --- | --- | --- | --- |
| CR-001 | 22/09/2026 | Michael | FR-010 | List the access levels explicitly | Requirement was not testable while the levels were undecided | Requirements, RTM | Accepted |
| CR-002 | 22/09/2026 | Michael | FR-011 | Elaborate on which access levels may see what | Same reason as CR-001 | Requirements, RTM | Accepted |
| CR-003 | 23/09/2026 | Michael | Section 6 RTM | Split the matrix into 6.1 (M1) and 6.2 (M2) | Readability, and to show M2 evidence separately from the M1 baseline | Traceability only | Accepted |
| CR-004 | 23/09/2026 | Michael | Section 5 | Added constraint IDs and CON-007 technology environment | Constraints could not be referenced; Master Brief section 25 makes the team responsible for checking technology availability on the BC Desktop | Constraints, ASRs, D-007 | Accepted |
| CR-005 | 23/09/2026 | Jared | Section 2 | Added the ASR influence column | Links stakeholders to the drivers they cause, as Milestone 2 section 5.2 requires | Stakeholder analysis, section 4.3 | Accepted |
| CR-006 | 23/09/2026 | Michael | Section 4 | Added 4.3 Architecturally Significant Requirements and Quality Drivers | Milestone 2 requires ASRs to be identified and linked to decisions | Requirements, architecture, RTM | Accepted |
| CR-007 | 26/09/2026 | Xander | Section 7 | Restructured the register one risk per table and raised R-008 to R-016 | Register must be reviewed at every milestone; new risks arise from the M2 decisions | Risk, deployment, testing | Accepted |
| CR-008 | 26/09/2026 | Xander | Section 9 | Restructured the log one decision per table, closed D-004 and D-005, added D-006 to D-015 | Decisions made in M2 had no records, and the log was unreadable as a single table | Architecture, data, technology, design, deployment | Accepted |
| CR-009 | 26/09/2026 | Jared | FR-010, FR-011 | Access levels reduced to three: Requester, Staff, Management. Administrative functions are handled by Management for the MVP; a separate Admin role moves to deferred scope | The data model, policies and UI in Section 13 are built on three roles, and a fourth undefined role cannot be tested | Requirements, data model (users.role), D-012, RTM, UI | Accepted |
| CR-010 | 26/09/2026 | Xander | FR-017, Section 8 FEC 2 | Adopt the status set open, assigned, in_progress, resolved, closed, with transitions seeded in a lookup table | FR-017 requires pre-defined options, and D-008 cannot enforce transitions without a fixed set | Requirements, data model, UI, D-015 | Accepted |
| CR-011 | 26/09/2026 | Jared | Section 3.1, FR-004, FR-007 | Confirm that email notification of a status change is in scope. Push notifications remain deferred | Section 3.4 already names email as the affordable replacement for WhatsApp, and D-009 and D-011 depend on it | Scope, design, deployment (queue worker), R-009 | Accepted |
| CR-012 | 26/09/2026 | Michael | FR-008, FR-016, FR-020 | One retention wording: records are purged 5 years after the last update, not 5 years after creation | Section 4 and the RTM contradicted each other. The full history must be kept until the whole record expires. | Requirements, data model, retention job | Accepted |
| CR-013 | 26/09/2026 | Michael | NFR-001 | Reword to bcrypt password hashing with a cost factor of 12 | “12 rounds of encryption” is not testable and confuses hashing with encryption | Requirement wording, M3 test evidence | Accepted |
| CR-014 | 26/09/2026 | Xander | Section 8 | Added Milestone 2 status and resolution columns, and raised FEC 7 and FEC 8 | Forward considerations must show progress, and deferring construction created a new one | Forward considerations, risk | Accepted |
| CR-015 | 26/09/2026 | Jared | Section 12 | Added the Milestone 2 readiness checklist beside the Milestone 1 list | The M1 checklist does not cover the M2 baseline | Checklist only | Accepted |
| CR-016 | 26/09/2026 | Michael | Section 6.2 | Extended the M2 matrix with implementation evidence, verification evidence and status columns | Milestone 2 section 4.2 requires these columns, with a controlled status where evidence does not yet exist | Traceability, M3 planning | Accepted |
| CR-017 | 26/09/2026 | Jared | D-006, D-007, Sections 13.1, 13.5, 13.6, 13.7, R-010, R-016 | Presentation layer changed from a separate React SPA over a Laravel JSON API to React and TypeScript rendered through Inertia. | The section 13.3.3 matrix ranked B-009 (Laravel + Inertia) highest. One deployable with server-side session authentication removes CORS and token handling, and no requirement needs an independent client or independent scaling (Assignment 2, Task 3). | Architecture, deployment topology, authentication (D-012), interfaces, UI structure; R-010 reduced; R-016 raised. | Accepted |
| CR-018 | 27/09/2026 | Jared | FR-005, FR-013, FR-021, FR-022, NFR-007, NFR-008 | Wording changed so each requirement is testable and matches the design. | FR-005’s title and criteria disagreed; FR-013 said filters remove relevant entries; FR-021 described deletion although resolution is a status change; FR-022 was not testable; the 95% targets were not supported by the cited source. | Requirements, RTM 6.1, M3 test design. | Accepted |
| CR-019 | 27/09/2026 | Jared | Section 4.1 note, ASR-005, CR-012 reason, references | Basis for the 5-year retention changed from RICA to a stakeholder decision balanced against POPIA section 14. | RICA section 30 applies to telecommunication service providers, which CivicConnect is not. | Requirement wording, ASR-005, reference list. | Accepted |
| CR-020 | 10/10/2026 | Michael | Section 6.2 | Changed an error in that all functions should be within three clicks of the main screen, not two. | A mistyping of the NFR, as it contradicted the NFR in section 4.2. | Potential miscommunication has been removed | Proposed |
| CR-021 | 12/10/2026 | Michael | Section 13.2.2 | Updated the ERD to reflect the actual tables and entities. | Laravel makes use of standard tables and entity names which was not accounted for in the initial ERD. | Can influence the SQL statements of the application. | Proposed |
| CR-022 | 12/10/2026 | Michael | Sections 6.3 and 13.2.6 | Added new sections to contain the work from milestone 3 | Test data became available and decisions were made. | Additional evidence. | Proposed |
| CR-023 | 13/10/2026 | Michael | Section 13.2.1 | Included template tables added by Laravel. | Laravel added additional template tables not considered. | Additional information | Proposed |
| CR-024 | 13/10/2026 | Michael | Sections 9, 13.7.4, 13.7.5, 13.3.6 | D-016 added: NEON selected as database host, | D-013 defered the provider for hosting the Application | Closes the database section of OD-01 | Proposed |
| CR-025 | 13/10/2026 | Michael | Section 13.7.1, AS-002, R-013 | Development database changed from Docker Compose to a locally installed PostgreSQL 18 | A locally installed PostgreSQL will match the NEON database’s version directly | Development/staging version parity is kept | Proposed |
| CR-026 | 13/10/2026 | Michael | R-002, R-0 Section 9 13 | Milestone 3 reviews added of the NEON limits and the verification of the staging. | Database provider has been chosen and tested | Causes the risk to reflect the real limits | Proposed |
| CR-027 | 13/10/2026 | Michael | Sections 9 13.7 intro and 13.7.1 | D-017 added, deferring the hosting of the application to milestone 4. | Milestone 3 allows for a simulated Staging of the application and database. | Application host part of OD-01 open until M4 | Proposed |
| CR-028 | 13/10/2026 | Michael | Section 6.1 | Acceptance criteria corrected to match Section 4.1 | FR-003 repeated FR-004’s criterion | Traceability only | Proposed |
| CR-029 | 15/10/2026 | Michael | Sections 9, 5.2, 7, 13.7, 13.8 | D-019 added. | Resend selected as mail provider, closing OD-02. | Clarity in scope, design and deployment | Proposed |
| CR-030 | 15/10/2026 | Michael | Sections 9, 13.6.5, 13.7.2, 13.8 | Sections 13.6.5, 13.7.2 updated for Resend over HTTPS | New information became available. | Clarity in scope, design and deployment | Proposed |
| CR-031 | 16/10/2026 | Michael | Submission Block. Sections 14-16 | Added the submission block and sections 14-16 | New information became available. | Tracibility | Proposed |

## Baseline Approval

| Project | CivicConnect |
| --- | --- |
| Baseline Type | Engineering Baseline (PED) |
| Version | 1.0 |
| Date | 09/09/2026 |
| Scope reviewed (Y/N) | Y |
| Requirements/traceability checked (Y/N) | Y |
| Repository/governance controls checked (Y/N) | Y |
| Outcome (ACCEPTED / CONDITIONALLY ACCEPTED / REVISION REQUIRED) | Conditionally accepted |

## Baseline Approval (Milestone 2)

| Project | CivicConnect |
| --- | --- |
| Baseline Type | Engineering Baseline (PED) |
| Version | 2.0 |
| Date | 30/09/2026 |
| Scope reviewed (Y/N) | N/A |
| Requirements/traceability checked (Y/N) | N/A |
| Repository/governance controls checked (Y/N) | N/A |
| Outcome (ACCEPTED / CONDITIONALLY ACCEPTED / REVISION REQUIRED) | N/A |

# 1. Problem Statement & Business Need

## 1.1 Problem Statement

A community-focused organisation CivicConnect currently manages their services requests such as facility faults, IT support, maintenance, lost property and security concerns across email, phone, WhatsApp, spreadsheets, and paper. This produces duplicated or lost requests, no visibility for requesters, no reliable reporting for management and no clear ownership for staff.

## 1.2 Business Need

CivicConnect needs a controlled digital platform that provides a reliable, traceable and usable way to submit, manage, monitor and report on service requests.

## 1.3 Intended Business Value

CivicConnect business value is a single controlled record of a request’s lifecycle. Submit to categorise to assign to act to resolve then report which closes the accountability gap that their current infrastructure has.

# 2. Stakeholder Analysis

| Stakeholder | Role / Description | Needs / Expectations | Influence | Interest | Potential Conflicts | ASR influence |
| --- | --- | --- | --- | --- | --- | --- |
| Requester | Community member submitting service requests | Visibility of request, Progress of request, Easy interface, Feedback | Low | High | Wants the request to be handled fast and wants full visibility | ASR-003, as the requester is harmed when requests are lost. |
| Staff | Actions and resolves requests | Clear ownership, interaction with requests | Medium | High | Admin overhead. Wants fewer notifications Could cause problems with requesters full visibility | ASR-001 and ASR-002, as the query response time and authorisation affect the staff. |
| Management | Oversight and reporting | Accountability, Reports, Overdue tracking | High | High | Wants detailed reporting which could conflict with staff's "less admin" preference | ASR-001 and ASR-002, as management requires access to all records. The Overdue tracking is also demanding on performance |
| System owner | Scoping the system | Scope and setting boundaries, Defendable system choices | High | High | Wants breadth of features while team has schedule and cost constraints | ASR-004, ASR-005, and ASR-006. The owner set the cost constraint, and is thus responsible for ASR-006, but retention conflicts with ASR-005 and a three-person team limits ASR-004 |
| Security team | Data handling | How the data is handled, Where the data is stored, How the data is stored, | Medium | High | May impact speed to make sure data is completely secured | ASR-002 and ASR-005, as the data requires authorisation, and raises a cross-cutting concern. |
| IT team | Service being requested | Alerted of request, Interaction with request, | Medium | Medium | Wants to be thorough with the request and requester wants to have it handled fast | ASR-002, as the IT support is a potentially sensitive category. Routing and restricting a request is thus governed by the IT team. |
| Lecturer | Oversees the life cycle of the application’s creation | As the client substitute, expects a working solution that satisfies the business need. As Assessor, expects traceable evidence to be continuously produced as the project progresses. | High | High | As the substitute for the client, they are the only source of clarification. However, information can be withheld to test the skills, understanding and judgement of the developers. As assessor they need access to the evidence. Time spent on evidence competes with time to create the application. | ASR-004. Maintainability is highly required, as the habits and continuously produced evidence for reviewability is highly required by the Assessor. |

# 3. Scope Baseline

## 3.1 In Scope

- Requests must be detailed such as category, location, area and short description

- Category must be selectable

- Staff be able to view, search, filter and sort requests and assign, accept, add comments, and update status

- Management must have a dashboard to view requests by status, category, overdue and basic activity reporting

- Role based access

- email notification of a status change

## 3.2 Out of Scope

- Native mobile app

- Multi-language support

- WhatsApp, SMS and or telephone integration

## 3.3 Deferred / Future Scope

- Push notifications

- Power BI style reporting to view advance analytics

- Separate Administrator role.

## 3.4 Defended Exclusion / Deferment

WhatsApp integration is excluded because it depends on a paid third-party API, which conflicts with the cost constraint (CON-003) and adds a reliability dependency. Status notifications are sent outside the customer’s 24-hour service window, so they must use utility template messages, which Meta charges per message (Meta, 2026). SMS and telephone integration are excluded for the same cost reason. Email notification of status changes, which is in scope (Section 3.1), meets the same need at no cost. Multi-language support is excluded because most translation services charge per word (Translated, 2025).

## 3.5 Scope baseline reviews and changes

The scope baseline was reviewed for PED v2.0. No capabilities were added or removed. One clarification was made under change control: CR-011 confirms that email notification of a status change is in scope, which Section 3.4 already anticipated when it named email as the affordable replacement for WhatsApp notification. Push notifications and Power BI style analytics remain in deferred scope. CR-009 reduced the access levels to three roles and moved a separate Administrator role to deferred scope (Section 3.3). Administrative functions are carried by Management for the MVP.

# 4. Requirements & Acceptance Criteria

## 4.1 Functional Requirements

All mentions of data being kept for 5 years is in accordance with the RICA compliance laws (VerifyNow, 2025). This is balanced against the POPIA act, section 14, where personal information should not be kept longer than necessary (POPIA, 2019).

| ID | Requirement | Source / Stakeholder | Priority | Acceptance Criteria |
| --- | --- | --- | --- | --- |
| FR-001 | Submission: being able to accept a new submission | Requester | High | The form used to submit must be saved into a database. |
| FR-002 | Submission: return of requested data | Requester | High | The requested data must be able to reach the requester. |
| FR-003 | Submission: Validation | Requester | Medium | Form submission must not be allowed if the form does not adhere to submission rules |
| FR-004 | Submission: feedback | Requester | Medium | Upon submission attempt, the user must receive feedback. If it’s an error, the problem must be stated. If successful, the user must be notified |
| FR-005 | Sort requests | Requester | Low | A requester can sort their requests by date submitted, date last changed or alphabetical order (changed by CR-018) |
| FR-006 | View Status: Accuracy | Requester | Medium | The status displayed must display the correct status. |
| FR-007 | View Status: Delay | Requester | Medium | From the moment the status is updated on the database, the viewer must be able to see the update if they were to refresh on their end |
| FR-008 | View History: Time data is stored | Requester | Low | A request and its related history, assignment and comment records are retained for 5 years after the last update, then purged automatically (changed by CR-012, v2.0) |
| FR-009 | View History: Amount | Requester | Medium | The Requester will see the last 50 requests per page. The Requester can go to other pages to see older requests. |
| FR-010 | Authentication | All users (Staff, management and requesters) | High | Users are assigned exactly one of three roles: Requester, Staff or Management. A user may only reach data permitted to that role (changed by CR-009, v2.0) |
| FR-011 | Authorised requests by staff | Staff | Medium | A Requester sees only their own requests. Staff see unassigned requests and requests assigned to them, not those assigned to other staff. Management sees all requests. Verified by a test per role and endpoint (changed by CR-009, v2.0) |
| FR-012 | Views provide relevant information | Staff | Low | The views should provide enough information in order to make relevant decisions. Examples being: category, status, time submitted, who is assigned to the request. |
| FR-013 | Search, filter and sort | Staff/Management | Low | Search returns every matching request the user is authorised to see; a filter removes non-matching requests; sort orders results by the chosen column (alphabetical, last updated, etc.). No combination of search, filter and sort causes an error or shows unauthorised data (changed by CR-018) |
| FR-014 | View full details | Staff | Medium | Tying in with the previous requirement, the view must be expandable to access more information on the request. A change history should also be accessible. |
| FR-015 | Assign/Accept responsibility | Staff | High | Staff should be able to assign requests to themselves. They should also be able to offer requests to others, and accept requests offered to them. |
| FR-016 | Request accountability | Staff | Low | Every assignment, offer and acceptance is recorded with the staff member and timestamp and retained for 5 years after the request’s last update, then purged automatically (changed by CR-012, v2.0). |
| FR-017 | Request update validation | Staff | Low | A status may only change to one of the seeded values open, assigned, in progress, resolved or closed, and only along a transition listed in the transition table (changed by CR-010, v2.0) |
| FR-018 | authorisation of request update | Staff | Medium | Only authorised staff should be allowed to make updates. For example, staff should not be allowed to change the status of a request not assigned to them. |
| FR-019 | Controlled transitions | Staff | Low | Every status change records the staff member and timestamp; the history is retained for 5 years after the request’s last update (changed by CR-012, v2.0). |
| FR-020 | Add comments/resolution information | Staff | Medium | Staff can add comments and resolution notes to a request; they are retained for 5 years after the request’s last update (changed by CR-012, v2.0). |
| FR-021 | Resolve Requests | Staff | High | When a request has been fulfilled, the assigned staff member can move it to Resolved. It leaves their active list but stays in the system with its full history (changed by CR-018) |
| FR-022 | View all information | Management | Medium | Management can view every request with its full status history, assignments and comments (changed by CR-018) |
| FR-023 | Identify overdue | Management | Low | Requests will have to be resolved within a set amount of time. Early estimates sets it at within 7 days. |
| FR-024 | Access information for performance analysis | Management | Low | Management should have access to the additional information given by the staff members in order to review the resolved requests. Basic analysis features, such as average time to resolution could also be added. |

## 4.2 Non-Functional Requirements

The following NFR’s are created making use of the ISO/IEC 25010 (ISO, 2023) standards for software product quality as reference.

| ID | Requirement | Category | Source | Priority | Acceptance Criteria |
| --- | --- | --- | --- | --- | --- |
| NFR-001 | Credential Storage | Security | Master Brief | High | Passwords are stored only as bcrypt hashes with a cost factor of 12; plain-text passwords are never stored or logged (changed by CR-013) |
| NFR-002 | Authorisation Enforced | Security | Master Brief, Requester | High | Users can only access data that they are allowed to access. For instance, a requester can’t access the credentials of other requesters |
| NFR-003 | Status Changes with user and timestamp | Security | Master Brief, Management | Medium | If a status change is made, an accurate timestamp must be made and the last user to change the status must be recorded. |
| NFR-004 | Result return time | Performance | Staff | Medium | For each 100 entries returned, there will be a maximum of 1 second wait time regardless of filters applied (Nielsen, 1993). This does not include Internet lag as we are not responsible for the internet connection. |
| NFR-005 | Availability | Reliability | Management | Medium | The application is available 99% of the time during operating hours, defined as 08:00-18:00, Monday to Friday (Tovarys, 2022). |
| NFR-006 | Data recovery | Reliability | Master Brief | Low | In case of data loss or overwriting, data must be able to be recovered/ rolled back within 48 hours |
| NFR-007 | Ease of use | Interaction capability | Requester | Low | At least 80% of test users submit a request without help on their first attempt (the average task-completion rate across studies is 78%). All functions are at most 3 clicks from the main screen (changed by CR-018) (Jeff, 2011). |
| NFR-008 | Validation failures produce actionable messages. | Interaction capability | Requester | Low | In a usability walkthrough, every validation message names the field concerned and states how to correct it (changed by CR-018) (Jeff, 2011). |
| NFR-009 | Code follows documented standards | Maintainability | Team | Medium | Every pull request merged to main has approvals from the two team members who did not author it, verified from the GitHub history. Code follows the standards in Section 10.2. |

## 4.3 Architecturally Significant Requirements and Quality Drivers

| ID | Requirement | Quality attribute | Significance | Measurable response | Decision reference |
| --- | --- | --- | --- | --- | --- |
| ASR-001 | NFR-004, FR-013 | Performance | The speed at which a response must be given is bound, with the “worst-case” query having a limit of 1 second response time per 100 records. This means that optimisation will be required, such as indexing. It also conflicts with the constraint of a free-tier service, as it caps connections and computational capacity. | For every 100 entries, regardless of filter combination, may not add more than 1 second to the search. | D-006 architecture, D-007 stack, D-013 deployment |
| ASR-002 | FR-010, FR-011, FR-013, FR-017, FR-018 | Security | Different roles will require different views on the same data. Searches and filters will also cause the security to be a dedicated layer instead of a set of guards on the code, meaning that it will highly affect the querying system. | No query made may return records outside the authorisation level of the specific user, regardless of the combination of filters applied. | D-002 audit history, D-012 authentication and RBAC, D-015 transitions |
| ASR-003 | FR-001, FR-002, NFR-005, NFR-006 | Reliability/ availability | A main issue CivicConnect is supposed to solve is requests being lost. Requests must be submitted, or a report must be given. Requests that has been stored must be recoverable when lost. | No submissions may be simply lost. Submission failures must be indicated, successful submissions must be acknowledged. Furthermore, overwritten data must be recoverable within 48 hours. 99% availability during operating hours is also required. | D-008 transactional write, D-011 notification integration, D-013 deployment |
| ASR-004 | NFR-009, Forward Engineering Consideration (FEC) | Maintainability | A three-person team on a fixed schedule with fixed milestones will have trouble with any re-work that may need to be done, and the FEC notes that retrofitting will be difficult and expensive to do. | Core workflow logic stays in service classes, and every change to main is approved by the two non-author team members before merging. | D-006 architecture, D-009 side-effect split, D-010 category strategy |
| ASR-005 | FR-008, FR-016, FR-019, FR-020 | scalability | The requirement of data needing to be stored for at least 5 years conflicts with the free-tier services that are required in the constraints. It also conflicts with the RICA laws, as data must be stored for at least 5 years. Furthermore, the POPIA act also requires the data to be deleted once the retention period ends. | Data cannot be lost or overwritten before the minimum 5 years due to limited storage. | D-008 persistence, D-013 deployment, CR-012 retention |
| ASR-006 | FR-008, FR-016, FR-019, FR-020, NFR-006 | Cost | CivicConnect needs to make use of free-tier software and services. This will mean that the 5-year retention rules will need to be able to handle the accumulated data over the 5 years without deleting anything. | Estimation and calculation of a 5-year data volume, and comparing it to the capacity provided by the free-tier services. Automated purges after 5 years. | D-007 stack, D-013 deployment, R-002 and R-013 free-tier limits |

# 5. Constraints

| ID | Category | Constraint | Engineering Implication |
| --- | --- | --- | --- |
| CON-001 | Scope | Exactly 3 registered students must deliver a controlled MVP covering requester, staff and management capabilities within the SEN381 timeline; once approved, committed scope must be baselined and controlled. | Every additional feature beyond the baseline (e.g. SMS notifications, map-based tagging) creates obligations to specify, secure, test and maintain it. Non-essential capabilities must go to Section 3.3 (Deferred/Future Scope) rather than be absorbed silently, to protect schedule and quality. |
| CON-002 | Schedule | The project must progress through four formal milestones (M1 - M4) within the SEN381 delivery period, each building on the previous approved baseline. | Requirements and early decisions made under this timeline must be evidence-based rather than rushed. Research must be timeboxed (as in Assignment 1) and baselined items may only be re-decided through a formal change record (Master Brief section 14), not informally. |
| CON-003 | Cost / Resources | The team should prefer free or low-cost services where practical but must identify their limitations and the likely operational cost beyond the educational context. | Free-tier hosting/database services typically cap storage, connection counts, request quotas or uptime, for example, Supabase’s free tier provides a 500 MB database and pauses projects after one week of inactivity (supabase, 2026).These limits must be documented during M2 technology research so the data model and expected request volume are sized realistically rather than assumed unlimited. |
| CON-004 | Quality | Quality attributes (e.g. traceability of request status, data accuracy, usability for non-technical requesters) must be defined now and later supported by measurable test/acceptance evidence. | NFRs must be written in testable terms at M1 (Section 4.2) - e.g. a measurable response-time or data-integrity condition - rather than as vague aspirations, so M3 testing has something concrete to verify against. |
| CON-005 | Security | Security is a lifecycle-wide responsibility. CivicConnect handles categories such as security concerns and IT support requests that may contain sensitive personal or safety-related information. | Access control (RBAC) and an audit trail must be treated as foundational requirements at M1 (see Forward Engineering Consideration #1 and #6, Section 8), not features added just before deployment - deferring this risks a costly late redesign of the data model and authentication approach. |
| CON-006 | Team Capability | Only three registered students must analyse, design, build, secure, test, deploy and individually defend the entire system (Master Brief section 8). | The team must weigh unfamiliar-but-powerful technology against realistic learning-curve risk within the schedule constraint above - this interaction is expanded in Section 5.1 and tracked as Risk R-001 (Section 7). |
| CON-007 | Technology environment | Tools must run on the BC Desktop or team laptops so the lecturer can assess the project in the institutional environment. Master Brief section 25 states the institution cannot guarantee that a chosen technology is available, so the team is responsible for checking this (R-014) | This helps the lecturer to assess the project on their end and to see how each part integrates with each other (the master brief also lists this as a requirement section 25) |

## 5.1 Constraint Interaction / Trade-off

Cost/Resources interacts directly with Security. The preference for free-tier hosting and database services (driven by the Cost constraint) is likely to mean weaker default network isolation, connection encryption or backup guarantees than a paid tier would provide. If the team selects a free-tier service purely because it is easiest to set up, without evaluating its security posture, the cost saving could increase security risk exposure for the sensitive request categories described in the Business Need (Section 1). This trade-off must therefore be evaluated explicitly in the M2 weighted technology decision matrix (Master Brief section 18.1) - security ecosystem is one of the required comparison criteria, rather than defaulting to whichever free service is fastest to configure under schedule pressure.

Schedule also interacts with Quality: because M1 - M4 are fixed and non-negotiable, a team that loses time to an unplanned issue (e.g. Risk R-001, technology learning curve) may be tempted to informally cut test coverage to protect the delivery date. The Master Project Brief (section 18) requires that any such trade-off be recorded and approved rather than silently absorbed, which is why Section 9 (Engineering Decision Log) and Section 7 (Risk Register) exist as controlled places to make that trade-off visible instead of hidden.

Milestone 2 outcome: the cost and security trade-off was resolved in D-007 and D-013 rather than left open. The selected stack is free and open source, and the deployment topology was deliberately reduced to one web process, one queue worker and one managed PostgreSQL instance so that the platform fits a free tier without weakening the security posture. Security ecosystem carried 12 of the 100 points in the section 13.3 weighted matrix, so the trade-off was scored rather than assumed. The remaining exposure is the hosting provider itself, which is tracked as R-002 and R-013 and closes with D-013

## 5.2 Assumptions and Dependencies

| ID | Assumption / dependency | Relied on by | If it proves false | Risk / decision | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- |
| AS-001 | The chosen free-tier host can run a persistent queue worker and Laravel’s scheduler (or a cron entry). | D-011, D-013, FR-008 | Notifications are queued but never sent; the retention purge never runs. | R-009, OD-01 | Michael | Closed. Render does not provide this in the free-tier service. The worker and scheduler has been replaced. |
| AS-002 | PHP 8.3+, Composer, Node.js and PostgreSQL can be installed and run on the BC Desktop or team laptops. | CON-007, D-007 | The project cannot be built or assessed in the institutional environment. | R-014 | Jared | Open - test at the start of M3 |
| AS-003 | Five years of request data fits within the free-tier database storage cap. | ASR-005, ASR-006, FR-008 | Storage fills before the retention period ends. | R-002, R-013 | Michael | Closed. 310 Seeded requests use around 1.08MB, meaning roughly 250 000 requests will fir inside NEON’s free tier service. |
| AS-004 | A free email provider allows enough daily sends for status notifications. | D-011, FR-007 | Notifications fail or need a paid plan. | OD-02, R-009 | Jared | Closed by D-019. Resend’s free tier allows 100 emails per day, enough for demonstration. |
| AS-005 | Every requester has an email address and a web browser. | Scope 3.1-3.2, FR-007 | Some requesters cannot receive notifications or use the platform. | R-007 | Xander | Assumed |
| AS-006 | Three roles (Requester, Staff, Management) are enough for the MVP. | CR-009, D-012 | Department sub-roles would change the policy layer and data model. | OD-03, R-003 | Jared | Assumed |
| AS-007 | Laravel 13, Inertia and the React starter kit stay supported for the project’s lifetime. | D-007, 13.3.6 | A forced upgrade or migration during construction. | R-001 | Xander | Assumed - Laravel 13 security fixes run to Q1 2028 |

6. Requirements Traceability Matrix (RTM)

## 6.1 Matrix filled by Milestone 1

| Req ID | Stakeholder /Source | Requirement Summary | Acceptance Criteria | Priority |
| --- | --- | --- | --- | --- |
| FR-001 | Requester | Submission: being able to accept a new submission | The form used to submit must be saved into a database. | High |
| FR-002 | Requester | Requested data is received | The requested data must be able to reach the requester from the database. | High |
| FR-003 | Requester | Input validation | Form submission must not be allowed if the form does not adhere to submission rules | Medium |
| FR-004 | Requester | Requester will receive feedback on submission | Upon submission attempt, the user must receive feedback. If it’s an error, the problem must be stated. If successful, the user must be notified | Medium |
| FR-005 | Requester | Requests can be categorised and sorted | On selection, requests must be categorise according to date submitted, date changed, or alphabetical order (Superseded by CR-018) | Low |
| FR-006 | Requester | Accuracy of status | The status displayed must display the correct status. | Medium |
| FR-007 | Requester | The status, upon update, must be visible to the requester | From the moment the status is updated on the database, the viewer must be able to see the update if they were to refresh on their end | Medium |
| FR-008 | Requester | The data must be stored for a set amount of time | The data must be stored for at least 5 years after the last update before it is automatically deleted (Superseded by CR-012) | Low |
| FR-009 | Requester | The requester must be able to view more than one request at a time | The Requester will see the last 50 requests per page. The Requester can go to other pages to see older requests. | Medium |
| FR-010 | All users of the system | User Authentication | Users can only access data that corresponds with their access levels/roles. These levels are still to be decided (Superseded by CR-009) | High |
| FR-011 | Staff | Authorised requests by staff | When the rules/authority levels are set, test to see that all users can only see what they are authorised to see (Superseded by CR-009) | Medium |
| FR-012 | Staff | Views provide limited but relevant information for quick overview | The views should provide enough information in order to make relevant decisions. Examples being: category, status, time submitted, who is assigned to the request. | Low |
| FR-013 | Staff/ Management | Search, filter and sort features | Search shows all valid data entries, filter removes all relevant data entries, and sort correctly sorts the data according to choice (alphabetical, last updated, etc.). Combinations of sorting, filtering and searching should not cause errors or show unauthorised data. (Superseded by CR-018) | Low |
| FR-014 | Staff | View full details on demand | Tying in with the previous requirement, the view must be expandable to access more information on the request. A change history should also be accessible. | Medium |
| FR-015 | Staff | Assign/Accept responsibility of a request | Staff should be able to assign requests to themselves. They should also be able to offer requests to others, and accept requests offered to them. | High |
| FR-016 | Staff | Accountability of handling request | Assignments should be recorded and stored in the database for review. These recordings should stay for only 5 years before deletion. (Superseded by CR-012) | Low |
| FR-017 | Staff | Update validation of Requests | Status updates can only be changed to pre-defined options. (Superseded by CR-010) | Low |
| FR-018 | Staff / Management | authorisation of request update | Only authorised staff should be allowed to make updates. For example, staff should not be allowed to change the status of a request not assigned to them. | Medium |
| FR-019 | Staff | Controlled transitions | If updates are made, the staff member and timestamp must be recorded, and stored for 5 years. (Superseded by CR-012) | Low |
| FR-020 | Staff | Add comments/resolution information | Staff should be able to add additional information to requests, and this should also be saved for 5 years in the database. (Superseded by CR-012) | Medium |
| FR-021 | Staff | Resolve Requests | When a request has been fulfilled, staff should be able to remove the request from their assigned requests (Superseded by CR-018) | High |
| FR-022 | Management | View additional information | Management will likely need full access to all information in the database. (Superseded by CR-018) | Medium |
| FR-023 | Management | Identify overdue requests | Requests will have to be resolved within a set amount of time. Early estimates sets it at within 7 days. | Low |
| FR-024 | Management | Access information for performance analysis | Management should have access to the additional information given by the staff members in order to review the resolved requests. Basic analysis features, such as average time to resolution could also be added. | Low |

## 6.2 Matrix filled by Milestone 2

| Req ID | ASR | Module / component | Data and persistence impact | Design / interface decision | Technology and decision reference | Implementation evidence | Verification evidence | Status |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| FR-001 | ASR-003 | Submission | Inserts a row in service_requests; commits before the response is returned | Controller validates, then delegates to the submission service | D-006, D-007, D-010 | Planned M3: RequestSubmissionService | Planned M3: submission feature test | Approved, not yet implemented |
| FR-002 | ASR-003 | RequestQuery | Reads service_requests only | Reads go through the data-access layer, not ad hoc queries | D-006, D-007 | Planned M3: requester list page | Planned M3: feature test | Approved, not yet implemented |
| FR-003 | ASR-003 | Submission | Constraints enforced by schema and validation rules | Validation contract in the form request, merged with category rules | D-007, D-010 | Planned M3: StoreServiceRequest | Planned M3: validation test | Approved, not yet implemented |
| FR-004 | ASR-003 | Submission | None; no write of its own | Response always returns a confirmation or a specific field error | D-007, CR-011 | Planned M3: submission response handling | Planned M3: feature test | Approved, not yet implemented |
| FR-005 | ASR-001 | RequestQuery, Category handling | Sorting applied to indexed columns | Sorting applied in the query, not in the client | D-001, D-010 | Planned M3: query scopes | Planned M3: sorting test | Approved, not yet implemented |
| FR-006 | ASR-002 | StatusAudit | Current status must agree with the history | One source of truth for status | D-002, D-008, D-015 | Planned M3: RequestStatusService | Planned M3: consistency test | Approved, not yet implemented |
| FR-007 | ASR-003 | StatusAudit, Notification | New status visible on the next read | Notification consumes the event; it is not a step inside the update | D-009, D-011, CR-011 | Planned M3: RequestStatusChanged event | Planned M3: listener test | Approved, not yet implemented |
| FR-008 | ASR-005, ASR-006 | Retention | Records purged 5 years after last update | Scheduled purge command | CR-012, D-013 | Planned M3: purge command | Planned M3: retention test | Approved, not yet implemented |
| FR-009 | ASR-001, ASR-002 | RequestQuery | Indexed pagination, 50 rows per page | Pagination mandatory on every list view | D-007 | Planned M3: paginated queries | Planned M3: pagination test | Approved, not yet implemented |
| FR-010 | ASR-002 | Authentication | users.role holds one of three roles | Session authentication; policies applied at the data layer | D-012, CR-009 | Planned M3: authentication scaffolding | Planned M3: login and role tests | Approved, not yet implemented |
| FR-011 | ASR-002 | Authorisation | Role determines which rows are visible | Enforced in the data layer, not per screen | D-012, CR-009 | Planned M3: ServiceRequestPolicy | Planned M3: policy test per role | Approved, not yet implemented |
| FR-012 | ASR-001 | RequestQuery | Reads only the fields the summary needs | Summary view separate from the detail read | D-006 | Planned M3: list page props | Planned M3: feature test | Approved, not yet implemented |
| FR-013 | ASR-001, ASR-002 | RequestQuery, Authorisation | Filters and sorts scoped by authorisation | Sortable columns whitelisted; authorisation applied in the query | D-012 | Planned M3: query builder | Planned M3: combination and authorisation tests | Approved, not yet implemented |
| FR-014 | ASR-002 | StatusAudit | Detail read includes the change history | Detail page receives history with the request | D-002 | Planned M3: detail page props | Planned M3: feature test | Approved, not yet implemented |
| FR-015 | ASR-004 | Assignment | Writes request_assignments rows | Offer and accept workflow rather than direct reassignment | D-006 | Planned M3: AssignmentService | Planned M3: assignment test | Approved, not yet implemented |
| FR-016 | ASR-002, ASR-005 | Assignment, StatusAudit | Assignment history retained for 5 years after last update | Assignment changes recorded the same way status changes are | D-002, CR-012 | Planned M3: assignment history | Planned M3: retention and audit test | Approved, not yet implemented |
| FR-017 | ASR-002 | StatusAudit | Status limited to the seeded enumeration | Transition validated in the service and backed by a database constraint | D-015, CR-010 | Planned M3: transition table and enum | Planned M3: illegal transition test | Approved, not yet implemented |
| FR-018 | ASR-002 | Authorisation, StatusAudit | Authorisation checked before the write commits | Policy check on the service call path | D-012 | Planned M3: policy in transition path | Planned M3: unauthorised update test | Approved, not yet implemented |
| FR-019 | ASR-002, ASR-005 | StatusAudit | Append-only history with actor and timestamp | Audit row written inside the same transaction as the status change | D-008, D-009 | Planned M3: RequestStatusService transition | Planned M3: StatusTransitionTest | Approved, not yet implemented |
| FR-020 | ASR-005 | StatusAudit | request_comments retained 5 years after last update | Adding a comment is an audited action | D-002, CR-012 | Planned M3: comment creation | Planned M3: feature test | Approved, not yet implemented |
| FR-021 | ASR-002 | Assignment, StatusAudit | Resolution is a status change, not a deletion | Resolve is a transition; the request stays in the system | D-015 | Planned M3: resolve action | Planned M3: transition test | Approved, not yet implemented |
| FR-022 | ASR-002 | Authorisation, Reporting | Reads the same tables at management scope | Same query path, wider authorisation scope | D-012 | Planned M3: management scope | Planned M3: scope test | Approved, not yet implemented |
| FR-023 | ASR-001 | Reporting | Overdue derived from timestamps, not stored | Overdue computed on read so the threshold can change | D-003 | Planned M3: reporting query | Planned M3: overdue test | Approved, not yet implemented |
| FR-024 | ASR-001 | Reporting | Aggregates over the status history | On-demand report rather than a live dashboard | D-003 | Planned M3: summary report | Planned M3: reporting test | Approved, not yet implemented |
| NFR-001 | ASR-002 | Authentication | Password hashes only, never plain text | bcrypt with cost factor 12 | CR-013, D-012 | Planned M3: hashing configuration | Planned M3: hash verification test | Approved, not yet implemented |
| NFR-002 | ASR-002 | Authorisation, RequestQuery | Authorisation applied on every read | Cross-cutting policy layer rather than per-screen guards | D-012 | Planned M3: policy layer | Planned M3: policy test matrix | Approved, not yet implemented |
| NFR-003 | ASR-002 | StatusAudit | Actor and timestamp recorded per change | Recorded inside the transaction | D-008 | Planned M3: history writes | Planned M3: audit field test | Approved, not yet implemented |
| NFR-004 | ASR-001 | RequestQuery | Indexes sized against a 5-year data volume | Pagination plus indexes on status, due date and assignee | D-007 | Planned M3: migrations with indexes | Planned M3: timed query check | Approved, not yet implemented |
| NFR-005 | ASR-003 | Deployment | Availability depends on the chosen host | Single instance accepted as a point of failure at MVP | D-013 | Planned M3: deployment configuration | Planned M4: availability observation | Approved, not yet implemented |
| NFR-006 | ASR-003, ASR-005 | RequestQuery, Deployment | Backups consume the storage allowance | Host backup or a scheduled database dump | D-013 | Planned M3: backup configuration | Planned M3: restore rehearsal | Approved, not yet implemented |
| NFR-007 | Not architecturally significant | UI | None | Every screen within three clicks of the landing view | D-006 | Planned M3: navigation structure | Planned M3: click-path walkthrough | Approved, not yet implemented |
| NFR-008 | ASR-004 | Submission, UI | None | Field-level validation messages returned with the response | D-007 | Planned M3: error handling | Planned M3: validation message test | Approved, not yet implemented |
| NFR-009 | ASR-004 | Repository governance | None | Two-reviewer approval before merge | Section 10, D-014 | In progress: pull request history | Planned M3: review evidence in PRs | In development |

## 6.3 Matrix filled by Milestone 3

| Req ID | Acceptance criteria | Implementation/ component | Test cases | Expected results | Technology and decision reference | Implementation evidence |
| --- | --- | --- | --- | --- | --- | --- |
| FR-001 | The submitted form is saved in the dataabase | StoreServiceRequest; ServiceRequestController::store saves the request and its first history row (open) in one transaction. | Automated tests: SubmitRequestTest: "a signed-in user can submit a request", "guests cannot submit a request". TC-E2E-01 (submit step). | The request is stored with the requester, status open and one history row. A guest is sent to the login page. | Laravel 13, PostgreSQL. D-002, D-008. | TC-E2E-01 passes the submit step. |
| FR-002 | The requested data reaches the requester. | requests/index (own list) and requests/show (detail with history and comments). | RequestVisibilityTest: "the list shows each role only what it may see" (requestor case), "the detail page is only open to users who may see the request" (own = 200). | A requester sees their own request in the list and can open its detail page. | Inertia + React pages. D-006, D-012. | Manuall inspection of the application. Signed in as a requestor, staff, and manager. |
| FR-003 | If the form does not adhere to the submission rules, it must be rejected | Schema prototype and the planned form validation. | Schema check test | A valid request is stored. Invalid inputs causes the request to be rejected. | Schema_check_tests .sql file for tests, schema_check_tests _output.docx contains outputs. | No defects found |
| FR-004 | On submission the user gets feedback: the problem if it fails, a confirmation if it succeeds. | Custom messages in StoreServiceRequest. | Automated tests TC-E2E-01 ("Request submitted" message). | A success message with the CC- reference after saving; field-level messages after a failure. | Inertia flash props. CR-011 (email part tracked under FR-007). | TC-E2E-01 shows the message. |
| FR-006 | The displayed status is the correct status. | Status column on service_requests; StatusBadge component. History rows written with each change. | Automated test: status-badge.test.tsx. TakeRequestTest: "staff can take an open, unassigned request" | The badge shows the stored status | D-002, D-008, D-015. | Success on automated tests. Partially implemented, as it only Take changes status so far. |
| FR-007 | After a status update, a refresh shows the new status (and the requester is emailed, CR-011). | Every page load reads the database (no caching). Email: Resend transport configured (D-019). NotifyRequesterOfStatusChange listener on RequestStatusChanged (D-011), merged in PR #24. | Email: manual test 15/10/2026, redirected by MAIL_DEMO_TO and delivered. | The new status shows on the next read. A test email arrives in the demo inbox. | Laravel Mail, Resend. D-011, D-019. | Email delivers to correct email address. |
| FR-008 | Records are retained for 5 years after last update, then automatically purged | On Delete restriction on foreign keys | 7 Schema check test | Users, categories, requests and transitions still referenced by other rows cannot be deleted or renamed. | Schema_check_tests .sql file for tests, schema_check_tests _output.docx contains outputs. | Implemented. Records are protected from premature deletion , and a scheduled deletion is added. |
| FR-009 | The requester sees 50 requests per page and can page back to older ones. | erviceRequestController::index uses paginate(50); Pagination component. | No automated test. Personally inspected the front end. | Page 1 shows at most 50 rows with links to further pages. | D-006. | Personally inspected the front end. Implemented |
| FR-010 | Users are only assigned one role, and must have one role at minimum | Checks on role options. Role defaults to requestor. | 2 Schema check tests | A role outside the decided options are rejected, and a new user receives “requestor” as default | Schema_check_tests .sql file for tests, schema_check_tests _output.docx contains outputs. | No defects. |
| FR-011 | Requesters see only their own requests; staff see unassigned ones and their own assignments; management sees all. | ServiceRequest::scopeVisibleTo() for lists; ServiceRequestPolicy::view() for detail pages. | RequestVisibilityTest: list per role (3 cases) and detail page (6 cases). CommentTest: "a user who cannot see a request cannot comment on it". | Each role gets exactly its expected set; a forbidden detail page returns 403. | Decision table (role x assignment state). D-012, ASR-002. | All features passed the automated tests. implemented. |
| FR-012 | Views show enough to decide: category, status, time submitted, assignee. | Request list columns: reference, category, location, status (with Overdue badge), assignee, last updated. | No automated test; checked in TC-E2E runs. | All listed fields appear on every row. | D-006. | Implemented; verified manually. |
| FR-013 | Search, filter and sort show only authorised matches without errors. | Search (q), status, category and date filters, "assigned to me"; all applied on top of scopeVisibleTo(). Sorting not built. | filter-bar.test.tsx (3). workflow.test.ts: "cleanFilters" (2). | Only filled-in filters are sent; results stay inside the user's visible set. | D-012, ASR-002. | All automated tests pass. Partially implemented: sorting not built. |
| FR-014 | A request can be expanded to full details, including its change history. | requests/show with history and comments. | RequestVisibilityTest (detail access). TakeRequestTest: "the detail page offers Take only when it is allowed". | Authorised users see details and history; others get 403. | D-002. | All automated tests passed. Implemented |
| FR-015 | Staff can assign requests to themselves, offer requests to others and accept offered requests. | State checks on the request assignments, and self assignments | 5 Schema check tests. | Offers, self assignments and acceptances are stored. Invalid stated are rejected. | Schema_check_tests .sql file for tests, schema_check_tests _output.docx contains outputs. | No defects. |
| FR-016 | All assignments, offers and acceptances are recorded with a timestamp. | Offers via foreign keys. Does not allow NULL values, Checks responds after creation. On Delete restrictions | 3 Schema check tests | Responses dated before its offer and offers/assignments without a valid staff member are rejected. Staff members with assignments cannot be deleted. | Schema_check_tests .sql file for tests, schema_check_tests _output.docx contains outputs. | No defects, Purge after 5 years not yet tested. |
| FR-017 | Status changes are only allowed to change to the set values, and can only transition along a transaction pipeline. | Checks on the status, the new status and old status. Five listed transitions. | 6 Schema check tests | Statuses outside the list are rejected. Statuses not adhering to the pipeline are also rejected. | Schema_check_tests .sql file for tests, schema_check_tests _output.docx contains outputs. | No defects. |
| FR-018 | Only authorised staff can update a request. | ServiceRequestPolicy::take. | TakeRequestTest: "only staff may take a request", "a request that is already assigned cannot be taken". | Non-staff and other staff get 403; nothing changes. | D-012. | all automated tests pass. Partially implemented: status updates not built. |
| FR-019 | Status changes records the timestamp and the author. Retained for 5 years. | Updates the request status history when a change is made. | 5 Schema check tests | First entry from no status to open is allowed. Other starting options are rejected. Missing and invalid unputs are also rejected. | Schema_check_tests .sql file for tests, schema_check_tests _output.docx contains outputs. | No defects. |
| FR-020 | Staff can add comments and resolution notes to a request. Comments/notes are held for 5 years. | Checks cannot be null, and author links | 4 Schema check tests | Only valid comments are stored. Empty comments and comments made by unauthorised authors are reject. | Schema_check_tests .sql file for tests, schema_check_tests _output.docx contains outputs. | No defects. This should also allow additional security if a requestor gains access to the comments. |
| FR-021 | Assigned staff can change a fulfilled request to Resolved. The request remains inside the history logs. | Checks that requests has a timestamp saved when moved to Resolved. On Delete Restrictions. | 6 Schema check tests | Resolving and closing of requests are accepted if it has a timestamp. Changes to resolved or closed status are rejected without a timestamp. | .sql file for tests, schema_check_tests _output.docx contains outputs. | No defects. |
| FR-022 | Management can view every request with full history, assignments and comments. | scopeVisibleTo() and the policy allow management everything. | RequestVisibilityTest: management list (all 4) and detail of another staff member's request (200). | Management sees every request and its detail page. | D-012. | All automated test passed. Implemented. |
| FR-023 | Requests not resolved within 7 days are flagged as overdue. | ServiceRequest::OVERDUE_DAYS = 7; overdue scope; Overdue badge; dashboard count. | DashboardTest: "counts requests by status, category and overdue". status-badge.test.tsx: "shows an Overdue badge only when overdue". | A request created 10 days ago counts as overdue; newer ones do not. | Dashboard. FR-023 estimate. | all Automated tests pass. Implemented. |
| FR-024 | Management can review resolved requests; basic analysis such as average time to resolution. | DashboardController: counts by status and category, overdue count, category and date filters. | DashboardTest (category filter case). | Totals change with the category filter. | D-003. | All automated tests pass. Partially implemented: average time to resolution not built. |
| NFR-001 | Passwords are stored only as bcrypt hashes, cost factor 12. | Laravel bcrypt; BCRYPT_ROUNDS=12 in .env.example (tests use 4 for speed). | PasswordUpdateTest; seeded users hashed with bcrypt. | No plain-text password is stored. | CR-013. | Implemented; configuration evidence. |
| NFR-002 |  |  |  |  |  |  |
| NFR-003 | Accurate timestamps are made and the author is saved if a status change is made. | History logs are linked to an author via foreign key. Logs does not allow NULL values. | 1 Schema check test | History logs without a valid user are rejected. | .sql file for tests, schema_check_tests _output.docx contains outputs. | No defects. |

# 7. Risk Register

## 7.1 Index

| ID | Risk | Prob. | Impact | Priority | Owner | Status |
| --- | --- | --- | --- | --- | --- | --- |
| R-001 | Team lacks production experience with the selected stack | Med | High | High | Xander | Mitigating |
| R-002 | Free-tier hosting and database limits exceeded or discovered late | Med | Med | Med | Michael | Mitigating |
| R-003 | Inadequate role-based access control exposes request information | Low | High | High | Jared | Mitigating |
| R-004 | Uncontrolled scope creep | Med | Med | Med | Xander | Open |
| R-005 | Two-reviewer approval creates a review bottleneck | Med | Med | Med | Michael | Open |
| R-006 | AI-assisted work accepted without sufficient verification | Med | High | High | Jared | Open |
| R-007 | Duplicate, incomplete or miscategorised requests | Med | Med | Med | Xander | Mitigating |
| R-008 | Concurrent status edits lose an update | Med | High | High | Xander | Mitigating |
| R-009 | No background worker on the chosen free-tier host | Med | Med | Med | Michael | Accepted |
| R-010 | Session and CSRF misconfiguration | Low | Med | Med | Jared | Mitigating |
| R-011 | Status changed outside the service layer, bypassing the audit trail | Low | High | High | Xander | Mitigating |
| R-012 | Whole team learning PHP at the same time | Med | Med | Med | Michael | Mitigating |
| R-013 | Free-tier database pauses or fills during assessment | Med | Med | Med | Michael | Accepted |
| R-014 | Toolchain unavailable on the BC Desktop | Med | Med | Med | Jared | Open |
| R-015 | Stack unvalidated because construction was deferred | Med | High | High | Xander | Open |
| R-016 | Inertia coupling limits future non-browser clients | Low | Low | Low | Jared | Accepted |

R-001: Team lacks production experience with the selected stack

| Field | Record |
| --- | --- |
| Description | Team lacks prior production experience with the technology stack eventually selected in M2, causing slower-than-planned implementation in M3. |
| Cause | Limited prior exposure beyond coursework-level use of the relevant framework(s). |
| Probability | Med |
| Impact | High |
| Priority | High |
| Mitigation | Select the M2 stack using the required weighted decision matrix, explicitly weighting team capability/learning curve; build a small proof-of-concept before committing. |
| Contingency | Fall back to the more familiar of the two shortlisted M2 stacks if velocity targets are missed by the M3 checkpoint. |
| Owner | Xander |
| Status | Mitigating |
| Milestone 2 review | Stack selected on evidence in D-007 using the section 13.3 matrix, with team capability and framework learning weighted 20 of 100 combined. Named fallback is now bundle B-003, the same Laravel backend with Blade views, which replaces only the presentation layer. The proof-of-concept part of the mitigation is not yet done and is carried as R-015. |

R-002: Free-tier hosting and database limits exceeded or discovered late

| Field | Record |
| --- | --- |
| Description | Free-tier hosting/database limits (storage, connections, request quota) are exceeded or discovered too late, constraining deployment or demo reliability. |
| Cause | Cost constraint (Section 5) drives selection of free-tier services without upfront investigation of their limits. |
| Probability | Med |
| Impact | Med |
| Priority | Med |
| Mitigation | Document free-tier limits for shortlisted platforms during M2 research; size the data model and expected request volume against those limits before committing. |
| Contingency | Identify a low-cost upgrade path in advance so the team can react quickly if limits are approached before M4. |
| Owner | Michael |
| Status | Mitigating |
| Milestone 2 review | D-013 fixes the topology at one web process, one queue worker and one managed PostgreSQL instance, which is the smallest footprint that satisfies the design. Section 13.7.4 records the limits that interact with the 5-year retention rule. The specific provider is still open, so this risk stays open until D-013 is closed. |
| Milestone 3 Review | Reviewed on 10/10/2026. Database provider that is chosen is the free plan of NEON, based in the London region. Neon provides 1GB storage per project, and 100 computing hours per project per billing period, and suspends after 5 minutes without activity (NEON, 2026). |

R-003: Inadequate role-based access control exposes request information

| Field | Record |
| --- | --- |
| Description | Inadequate role-based access control exposes request information |
| Cause | RBAC is treated as an implementation detail rather than a first-class requirement at baseline. |
| Probability | Low |
| Impact | High |
| Priority | High |
| Mitigation | Define RBAC roles and access rules as explicit NFRs and acceptance criteria at M1 (Section 4.2); include access-control test cases in M3 security evidence. |
| Contingency | Conduct a focused access-control review before staging deployment; restrict production data exposure until verified. |
| Owner | Jared |
| Status | Mitigating |
| Milestone 2 review | D-012 places authorisation in ServiceRequestPolicy at the data-access layer rather than per screen, so the same rule applies to every query path. The policy test set is specified but not yet written, so the risk remains open until M3 evidence exists. The fourth ‘Admin’ level was resolved by CR-009: three roles for the MVP, with a separate Administrator role deferred. |

R-004: Uncontrolled scope creep

| Field | Record |
| --- | --- |
| Description | Uncontrolled scope creep (for example adding SMS notifications or a mobile app beyond the approved baseline) consumes time needed for core-capability quality. |
| Cause | Desire to appear comprehensive or impressive at milestone presentations. |
| Probability | Med |
| Impact | Med |
| Priority | Med |
| Mitigation | Enforce the scope baseline (Section 3); any proposed addition must pass through the Change Request/Impact Analysis template (Master Brief Appendix E) before implementation. |
| Contingency | Revert to baseline scope and formally defer the addition to future scope if schedule slippage is detected at a checkpoint. |
| Owner | Xander |
| Status | Open |
| Milestone 2 review | The control worked as intended: the only scope movement in M2, confirming that status-change email is in scope, went through the change record rather than being absorbed silently. No features were added beyond the M1 baseline. |

R-005: Two-reviewer approval creates a review bottleneck

| Field | Record |
| --- | --- |
| Description | With only three team members, the mandatory two-reviewer PR approval effectively requires unanimous team review of every substantive change, creating a review bottleneck or an incentive to rubber-stamp under time pressure. |
| Cause | Small team size relative to the two-approvals-from-non-authors governance control (Master Brief section 9). |
| Probability | Med |
| Impact | Med |
| Priority | Med |
| Mitigation | Agree review-turnaround expectations in the Team Working Agreement (Section 10.2); stagger substantive PRs rather than batching them near deadlines. Reviewers respond to a review request within 24 hours on weekdays. If a reviewer is unavailable for longer, the author records the delay on the pull request rather than merging without the second approval. |
| Contingency | If a bottleneck occurs, prioritise reviewing PRs that block others’ work and record the delay rather than silently skipping meaningful review. |
| Owner | Michael |
| Status | Open |
| Milestone 2 review | Still open. The risk grows in M3 when code review replaces document review, because all three members will be reviewing PHP none of them has written before. Record actual PR turnaround times from M3 so the exposure can be measured rather than estimated. |

R-006: AI-assisted work accepted without sufficient verification

| Field | Record |
| --- | --- |
| Description | AI-generated code, tests or requirement wording is accepted into the controlled baseline without sufficient independent verification, introducing a defect, incorrect assumption or security gap. |
| Cause | Schedule pressure encourages faster acceptance of AI output; verification takes time. |
| Probability | Med |
| Impact | High |
| Priority | High |
| Mitigation | Apply the AI Usage Register (Section 11) to every material AI contribution; the responsible student must test, cite or otherwise verify the specific claim before it enters the baseline. |
| Contingency | Treat any unverifiable AI-assisted claim as rejected by default rather than including it to save time. |
| Owner | Jared |
| Status | Open |
| Milestone 2 review | Register maintained through M2. The exposure changes in M3: verifying a factual claim in a document is cheaper than verifying generated PHP in a language none of the team has used, so AI-assisted code must be read line by line and covered by a test before merge. |

R-007: Duplicate, incomplete or miscategorised requests

| Field | Record |
| --- | --- |
| Description | Requesters submit duplicate, incomplete or miscategorised service requests, reducing staff’s ability to prioritise and increasing the perceived unreliability of the platform. |
| Cause | This is one of the core problems described in the CivicConnect business need; unconstrained submission would reproduce it. |
| Probability | Med |
| Impact | Med |
| Priority | Med |
| Mitigation | Design mandatory fields and a controlled category list into the functional requirements (Section 4.1) rather than leaving submission unconstrained. |
| Contingency | Allow staff to merge/relabel duplicate or miscategorised requests as a controlled, audited action. |
| Owner | Xander |
| Status | Mitigating |
| Milestone 2 review | Mitigation strengthened: category handling now goes through a dedicated CategoryHandler class per category, resolved from a CategoryRegistry keyed on the category code (D-010, Section 9). A request reclassified out of ‘Other’ is routed through its own handler rather than a conditional branch, so a reclassification cannot silently default to generic handling. |

R-008: Concurrent status edits lose an update

| Field | Record |
| --- | --- |
| Description | Two staff members open the same request and update its status at nearly the same time; the second write silently overwrites the first, so an action is lost and the audit trail records a state nobody intended. |
| Cause | Requests are visible to multiple staff members, and without a concurrency control the last write wins. |
| Probability | Med |
| Impact | High |
| Priority | High |
| Mitigation | D-008 adds an optimistic version column checked inside the transaction; a stale version raises StaleRequestException rather than overwriting. The user is returned to the request with its current state and asked to retry. |
| Contingency | If conflicts prove frequent in M3 testing, narrow the editable window by refreshing request state when the detail screen is opened, before considering heavier locking. |
| Owner | Xander |
| Status | Mitigating |
| Milestone 2 review | Raised at M2 from Assignment 2 Task 2 research. Design-level mitigation is in place; verification is a Milestone 3 feature test asserting that a stale version is rejected. |

R-009: No background worker on the chosen free-tier host

| Field | Record |
| --- | --- |
| Description | The selected free-tier host does not support a persistent background worker process, so queued status notifications are accepted by the application but never delivered. |
| Cause | D-011 makes notification delivery a queued listener, which requires a worker process that many free tiers do not provide. |
| Probability | Med |
| Impact | Med |
| Priority | Med |
| Mitigation | Make worker support a selection criterion when D-013 closes; confirm it before committing to a provider. |
| Contingency | Run the queue from a scheduled task using queue:work with a stop-when-empty flag, accepting delayed delivery, or send the notification synchronously after commit as a temporary measure. |
| Owner | Michael |
| Status | Accepted |
| Milestone 2 review | Raised at M2 as a direct consequence of D-011 and D-013. Remains open until the hosting provider is chosen in section 13.8. |
| Milestone 3 review | Reviewed 15/10/2026. Render's free tier has no background workers (D-018). Mitigated with the risk's own contingency: notifications are sent synchronously after commit, and the purge moves to a GitHub Actions schedule. Residual risk: a slower response while an email is sent, and no automatic retry. |

R-010: Session and CSRF misconfiguration

| Field | Record |
| --- | --- |
| Description | Session cookie or CSRF settings are wrong for a deployed environment, so users cannot log in, or protection against cross-site request forgery is weakened. |
| Cause | Session lifetime, cookie domain, secure flag and CSRF token handling differ between local development and a hosted environment. |
| Probability | Low |
| Impact | Med |
| Priority | Med |
| Mitigation | Keep all environment-specific values in environment variables (section 13.7.2); add a feature test covering login and an authenticated Inertia request so a broken configuration fails in CI rather than in the demo. |
| Contingency | Roll back to the last known-good environment configuration and verify against the CI test before redeploying. |
| Owner | Jared |
| Status | Mitigating |
| Milestone 2 review | Revised at M2. The original form of this risk covered CORS and cross-origin token handling for a separate SPA. D-006 and D-012 removed that boundary entirely, so the remaining exposure is ordinary session and CSRF configuration, which is smaller. Downgraded from High to Medium priority. |

R-011: Status changed outside the service layer, bypassing the audit trail

| Field | Record |
| --- | --- |
| Description | A controller, seeder, console command or future feature updates a request’s status directly through the model, skipping RequestStatusService, so no history row is written and the audit trail has a gap that cannot be reconstructed. |
| Cause | Nothing in the framework prevents a direct model update; the rule that only the service may change status is a convention. |
| Probability | Low |
| Impact | High |
| Priority | High |
| Mitigation | State the rule explicitly in the code standards, enforce it in review, and add a Milestone 3 test asserting that the count of history rows equals the count of status transitions for a request. |
| Contingency | If a gap is found, record it as a defect, backfill what can be reconstructed from application logs, and state plainly in the PED what cannot be recovered. |
| Owner | Xander |
| Status | Mitigating |
| Milestone 2 review | Raised at M2 from D-002, D-008 and Forward Engineering Consideration #3. Audit gaps cannot be backfilled after the fact, which is why the probability is low but the impact is high. |

R-012: Whole team learning PHP at the same time

| Field | Record |
| --- | --- |
| Description | All three members are learning PHP and Laravel simultaneously, with no member able to act as an internal reference, so early mistakes are less likely to be caught in review and rework is more likely. |
| Cause | D-007 selects a stack in a language none of the team has used, accepted deliberately as a trade-off. |
| Probability | Med |
| Impact | Med |
| Priority | Med |
| Mitigation | Pair on the first vertical slice rather than splitting unfamiliar work three ways; follow the official Laravel documentation and the official starter kit structure rather than mixed tutorials; keep the first PRs small so review is meaningful. |
| Contingency | Invoke the D-007 fallback to bundle B-003 if the first slice takes materially longer than planned. |
| Owner | Michael |
| Status | Mitigating |
| Milestone 2 review | Raised at M2 as a distinct exposure from R-001: R-001 is about stack experience generally, this is about having no internal expert to review against. |

R-013: Free-tier database pauses or fills during assessment

| Field | Record |
| --- | --- |
| Description | A free-tier PostgreSQL instance pauses after inactivity or approaches its storage cap, making the demonstration unreliable or blocking writes during assessment. |
| Cause | Free tiers commonly suspend idle databases and cap storage, which interacts with the 5-year retention requirement in FR-008. |
| Probability | Med |
| Impact | Med |
| Priority | Med |
| Mitigation | Record the chosen provider’s actual limits when D-013 closes; seed a small realistic dataset rather than bulk test data; warm the connection before presenting. |
| Contingency | Keep a local PostgreSQL environment ready as a demonstration fallback and state plainly that it is not the hosted environment. |
| Owner | Michael |
| Status | Accepted |
| Milestone 2 review | Raised at M2, related to R-002 but specific to demonstration reliability rather than to sizing. |
| Milestone 3 review | Reviewed on 10/10/2026. NEON’s free plan pauses idle databases after 5 minutes, and resumes on the next connection. This means in the demonstration there is a risk of slower first requests. A potential mitigation strategy is to “warm up” the connection before presentation. The NEON database has been staged successfully and verified with 53/53 successful tests. Render’s free web service also sleeps after 15 minutes without traffic, so the app must be given time to “warm up” as well. |

R-014: Toolchain unavailable on the BC Desktop

| Field | Record |
| --- | --- |
| Description | PHP, Composer, Node or PostgreSQL cannot be installed or run on the BC Desktop platform, so the project cannot be built or assessed in the institutional environment. |
| Cause | CON-007 and Master Brief section 25: the institution does not guarantee that a chosen technology is available or supported on its platform. |
| Probability | Med |
| Impact | Med |
| Priority | Med |
| Mitigation | Install and run the full toolchain on a BC Desktop machine and record the result in section 13.3 before construction begins. |
| Contingency | Develop on team laptops and document the limitation, or invoke the D-007 fallback if the difference blocks assessment. |
| Owner | Jared |
| Status | Open |
| Milestone 2 review | Raised at M2. Until the installation is verified, the dev-environment row of the section 13.3 matrix is an estimate rather than evidence. This is a few hours of work and should be closed early in M3. |

R-015: Stack unvalidated because construction was deferred

| Field | Record |
| --- | --- |
| Description | With no proof of concept built during M2, the assumptions behind D-007, D-008 and D-013 are untested, so a problem with the stack, the transaction design or the hosting topology would surface only in M3 under delivery pressure. |
| Cause | D-014 defers construction to M3, concentrating learning and delivery in the same window. |
| Probability | Med |
| Impact | High |
| Priority | High |
| Mitigation | Timebox a spike at the start of M3: create the Laravel project, connect it to PostgreSQL, run one migration and render one Inertia page, before committing to the full build order. |
| Contingency | If the spike reveals a blocking problem, invoke the D-007 fallback to B-003 and record the change through the change-control process. |
| Owner | Xander |
| Status | Open |
| Milestone 2 review | Raised at M2 alongside D-014. This is the direct cost of deferring construction and should be stated plainly in the defence rather than left implicit. |

R-016: Inertia coupling limits future non-browser clients

| Field | Record |
| --- | --- |
| Description | Because D-006 exchanges page props rather than a published API, a future mobile client or third-party integration would require a JSON API to be added before it could consume CivicConnect data. |
| Cause | Inertia couples the presentation layer to the application, which is the trade-off accepted in D-006 and D-007. |
| Probability | Low |
| Impact | Low |
| Priority | Low |
| Mitigation | Keep business rules in services rather than controllers so that adding routes/api.php later is additive rather than a rewrite. |
| Contingency | Add a JSON API alongside Inertia over the same services if a second client is ever required. |
| Owner | Jared |
| Status | Accepted |
| Milestone 2 review | Accepted at M2. No stakeholder requirement in the approved scope calls for a non-browser client, and the scope baseline excludes a native mobile app. |

# 8. Forward Engineering Considerations

|  | Concern | Why It Matters Now | Decision/Activity It Influences | Information Still Missing | Risk of Ignoring It | Milestone 2 status | Resolved by / next step |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Authentication & role-based access control (Requester / Staff / Management) | The three-role model is already implied by the minimum business capabilities (Master Brief section 3) and shapes which requirements, screens and data fields exist at all. | M2 authentication/architecture design, M2 data model, M3 security testing, M4 security evidence. | Whether staff need finer sub-roles (e.g. by department), and whether management needs read-only or configurable access. | Retrofitting access control after construction typically forces rework of the data model, API contracts and UI, with a higher chance of an overlooked authorisation gap. | Resolved for the three-role model; department sub-roles carried forward | D-012 and CR-009. Sub-roles reconsidered only if a stakeholder need appears |
| 2 | Controlled request category & status taxonomy | Several FRs (submission, filtering, reporting) and the quality/NFR constraint depend on a fixed, agreed vocabulary rather than free text. | M1 requirement wording, M2 data model, M4 management reporting. | The final list of categories/status values, and whether it must be extensible later without a code change. | Free-text categorisation reproduces the exact fragmentation problem CivicConnect is meant to solve; late taxonomy changes ripple through requirements, data and reports. | Resolved | CR-010 fixes the status set; D-001 and D-010 fix the category set and handling |
| 3 | Request audit trail / status-change accountability | The business need explicitly names 'weak accountability for changes to request status' as a current problem; the data model must capture who changed what and when from the outset. | M2 data/persistence design, M3 traceability evidence, M4 stakeholder validation of accountability. | Retention period for audit history and whether staff need full history or only current state. | Adding an audit trail after core tables are built typically requires a migration touching every write path; audit gaps found late cannot be backfilled. | Designed, not yet implemented | D-008 and D-009. Retention of audit history settled by CR-012; enforcement verified in M3 (R-011) |
| 4 | Deployment platform & environment strategy (dev/test/staging/production) | The cost constraint (free/low-cost preference) and the later need for staging-to-production parity (Master Brief section 17) both depend on understanding platform options and limits early. | M2 technology decision matrix, M3 staging deployment, M4 production release. | Concrete free-tier limits, and whether the eventual stack's hosting options support proper environment separation. | Discovering a platform incompatibility at M3/M4 could force an emergency migration under deadline pressure with no time to test properly. | Partly resolved: topology fixed, provider deferred | D-013. Provider selection closes in Section 13.8 before the M3 staging deployment |
| 5 | Testability of core workflows (submission → assignment → resolution) | If requirements and design don't anticipate automated testing (Master Brief section 15), M3's automated test evidence will be retrofitted and weaker. | M1 acceptance-criteria wording, M2 design decisions (e.g. avoiding tight coupling), M3 test strategy. | Which workflows are highest-risk and therefore deserve the earliest test coverage. | Untestable design decisions made in M2 (e.g. logic embedded directly in UI code) are expensive to unpick once construction is underway. | In progress | D-006 keeps business rules in services rather than the UI, which is what makes them testable; test set defined in Section 6.2, written in M3 |
| 6 | Sensitive-data handling for security/IT-support request categories | Some categories (security concerns, IT support) may contain sensitive information, which interacts directly with RBAC (Concern 1) and drives specific NFRs. | M1 NFRs (Section 4.2), M2 architecture (e.g. encryption at rest/in transit), M3 security review. | Whether any category needs restricted visibility even from general staff, not only from requesters. | Sensitive information could be exposed to unauthorised staff, leaving a residual security risk the team cannot honestly claim to understand at M4 (Master Brief section 23). | Partly resolved | D-012 applies authorisation at the data layer; encryption at rest depends on the provider chosen in D-013 |
| 7 | Application evidence and the start of construction | D-014 defers construction to Milestone 3, so the baseline is not yet backed by code and the end-to-end trace stops at the technology decision | M3 build order, Section 6.2 status values, criterion F evidence | How long the first vertical slice takes with a stack new to the team | Learning and delivery are compressed into the same window, and an unworkable assumption would surface late (R-015) | Open - construction deferred to Milestone 3 (D-014) | R-015 spike at the start of M3, then the first vertical slice covering FR-001, FR-017 and FR-019 |
| 8 | Staging and production parity | Master Brief section 17 expects staging to resemble production, and the queue worker required by D-011 must exist in both | D-013 provider selection, M3 staging deployment, M4 release | Whether the chosen free tier supports a persistent worker and environment separation | A platform that cannot run a worker would break notification delivery only after deployment (R-009) | Closed. The database will be hosted using NEON, the application will be hosted via Render. | OD-01 and OD-02; confirm worker and scheduler support before the M3 staging deployment (R-009, AS-001) |

# 9. Engineering Decision Log

## 9.1 Index

| ID | Decision | Status |
| --- | --- | --- |
| D-001 | Controlled request category vocabulary | Baselined M1; Later Consequence updated at M2 |
| D-002 | Append-only status history | Baselined M1; Later Consequence updated at M2 |
| D-003 | On-demand management reporting at MVP | Baselined M1; Later Consequence updated at M2 |
| D-004 (Deferred, now closed) | Technology-stack selection | Closed at M2; resolved by D-007 |
| D-005 (Deferred, now closed) | Deployment and hosting platform selection | Closed at M2; superseded by D-013 |
| D-006 | Architecture style | New at M2; option C (SPA) superseded by option B (Inertia) through CR-017 |
| D-007 | Technology stack selection | New at M2; closes D-004 |
| D-008 | Status change and audit write in a single transaction | New at M2 |
| D-009 | Splitting status-change side effects | New at M2; adapts the Assignment 2 recommendation |
| D-010 | Category-specific handling | New at M2 |
| D-011 | Status-to-notification integration mechanism | New at M2 |
| D-012 | Authentication and role-based access control | New at M2 |
| D-013 | Deployment direction and environment strategy | New at M2; supersedes D-005. Closed by D-016. Hosting of the application is deferred to D-017. |
| D-014 | Construction deferred to Milestone 3 | New at M2 |
| D-015 | Status taxonomy and controlled transitions | New at M2; closes Forward Engineering Consideration #2 |
| D-016 | Hosting service for the database. | New at M3. |
| D-017 | Hosting service for the application | New at M3 |
| D-018 | Chosen Hosting service for Application | New at M3, supersedes D-017 |

D-001: Controlled request category vocabulary

| Field | Record |
| --- | --- |
| Status | Baselined M1; Later Consequence updated at M2 |
| Context | CivicConnect requires a shared vocabulary for request types to enable consistent submission, staff triage and management reporting. |
| Constraints | Must stay simple for non-technical requesters; must cover the categories named in the business need (facility faults, damaged equipment, security concerns, IT support, maintenance, lost property), plus ‘Other’. |
| Alternatives | (a) Free-text field; (b) Fixed controlled list; (c) Fixed list with an ‘Other’ option requiring staff reclassification. |
| Decision | Adopt (c): a fixed controlled list with a staff-reclassifiable ‘Other’ category. |
| Rationale | Balances requester ease-of-use with the data-quality and reporting needs in the business need, without an over-rigid list that blocks legitimate edge cases. |
| Trade-offs | Slightly more implementation complexity than free text; requires a staff workflow for reclassifying ‘Other’ items. |
| Risks | If the list is poorly chosen, most requests may default to ‘Other’, undermining the benefit (linked to Risk R-007). |
| Evidence | Master Brief section 2 (fragmentation problem); Stakeholder Analysis, Section 2. |
| Later consequence | M2: realised as the categories table (section 13.2.1) and the per-category handlers of D-010. Reclassification of ‘Other’ is an audited staff action. |

D-002: Append-only status history

| Field | Record |
| --- | --- |
| Status | Baselined M1; Later Consequence updated at M2 |
| Context | Every service request must support staff and management accountability for status changes. |
| Constraints | It must remain technology-agnostic at M1. It must not assume a specific database engine. |
| Alternatives | (a) Store only current status. (b) Store current status plus a full append-only status-change history. |
| Decision | Adopt (b): every status transition is recorded as an immutable history entry (who, what, when). |
| Rationale | Directly addresses the ‘weak accountability’ problem in the business need and is required groundwork for the M3/M4 traceability and quality-evidence standards. |
| Trade-offs | Slightly larger data model and additional write operations per status change. |
| Risks | If not enforced consistently across every code path that changes status, gaps could appear in the audit trail (linked to Forward Engineering Consideration #3). |
| Evidence | Master Brief section 2 problem statement, and section 11 traceability standard. |
| Later consequence | M2: realised as request_status_history (section 13.2.1), written inside the D-008 transaction. The enforcement rule is set by D-009. |

D-003: On-demand management reporting at MVP

| Field | Record |
| --- | --- |
| Status | Baselined M1; Later Consequence updated at M2 |
| Context | Whether management reporting requires a real-time dashboard or a periodic/on-demand view at MVP stage. |
| Constraints | Must fit within the schedule constraint (Section 5) and the three-person team capability constraint. |
| Alternatives | (a) Real-time dashboard; (b) Periodic/on-demand report view. |
| Decision | Adopt (b) for MVP scope; defer (a) to future scope. |
| Rationale | Reduces architectural complexity and risk within the schedule constraint while still satisfying the minimum management capability of identifying open/overdue/resolved requests (Master Brief section 3). |
| Trade-offs | Less immediate visibility for management than a live dashboard would offer. |
| Risks | If stakeholders expected real-time visibility, this could become a change request later (Master Brief Appendix E). |
| Evidence | Scope Baseline, Section 3.3. |
| Later consequence | M2: realised as an on-demand reporting read path (Reporting component, section 13.1.1). No live dashboard has been introduced. |

D-004 (Deferred, now closed): Technology-stack selection

| Field | Record |
| --- | --- |
| Status | Closed at M2; resolved by D-007 |
| Context | Technology-stack selection for CivicConnect. |
| Constraints | Not applicable at the time of the M1 entry. |
| Alternatives | Not applicable at the time of the M1 entry. M2: the nine bundles compared in section 13.3.1. |
| Decision | DEFERRED to Milestone 2. M2: resolved by D-007. |
| Rationale | M1 explicitly excludes final technology-stack selection (Milestone 1 Brief section 5). A defensible choice requires the weighted decision matrix and evidence gathering scoped to M2 (Master Brief section 18.1), not yet performed at M1. |
| Trade-offs | Not applicable at the time of the M1 entry. |
| Risks | Delaying keeps options open but leaves less M2 time for the required comparison (linked to Risk R-001). Research must begin immediately after M1 submission. |
| Evidence | Not applicable at the time of the M1 entry. M2: section 13.3 matrices and D-007. |
| Later consequence | Superseded by D-007 on the date recorded in Document Control. |

D-005 (Deferred, now closed): Deployment and hosting platform selection

| Field | Record |
| --- | --- |
| Status | Closed at M2; superseded by D-013 |
| Context | Deployment/hosting platform selection. |
| Constraints | Not applicable at the time of the M1 entry. |
| Alternatives | Not applicable at the time of the M1 entry. M2: the options compared in D-013. |
| Decision | DEFERRED to Milestone 2, pending D-004. M2: superseded by D-013, which fixes the deployment topology and defers only the provider. |
| Rationale | Hosting compatibility depends on the technology stack chosen in D-004. Deciding hosting first would risk prematurely constraining that choice. |
| Trade-offs | Not applicable at the time of the M1 entry. |
| Risks | Free-tier limits (Risk R-002) must still be scoped generally now (Forward Engineering Consideration #4) even though the specific platform is deferred. |
| Evidence | Not applicable at the time of the M1 entry. M2: section 13.7 and D-013. |
| Later consequence | Provider selection remains open and is tracked in section 13.8. |

D-006: Architecture style

| Field | Record |
| --- | --- |
| Status | New at M2; revised to the Inertia presentation layer |
| Context | CivicConnect needs an architecture that enforces auditable status changes, and that applies authorisation consistently across queries. All this must be done within the free-tier service constraint. |
| Constraints | The cost constraint, as the services must be free. It needs browser-based access and must be buildable and maintainable by a 3-person team. |
| Alternatives | A server-rendered application without APIs (option A), a layered modular monolith with an Inertia-rendered React presentation layer (option B), a layered modular monolith with a separate React SPA over a Laravel API (option C), or distributed services (option D). |
| Decision | Option B, a layered modular monolith application using React and TypeScript rendered through Inertia over Laravel. There is no internal network boundary and no separate JSON API at this stage. |
| Rationale | Detailed justification and reasoning is in section 13.1.3. In summary: option D turns commits into distributed transactions and would exceed the free-tier constraint; option C satisfies the requirements but adds a network boundary, CORS handling, a second deployable and duplicated validation for a client the project does not need to serve independently, which is the cost Assignment 2 Task 3 warned against; option A is the simplest but leaves the team’s React and TypeScript skills unused. Option B keeps one deployable and server-side authorisation while still using React for presentation. |
| Trade-offs | The front-end and back-end deploy together and cannot be released independently. Page props are an internal contract, not a reusable API, so a future mobile or third-party client would require a JSON API to be added alongside Inertia. |
| Risks | R-001 and R-005, the boundaries may erode under the pressure of the project’s schedule. Presentation logic could leak into controllers if the component responsibilities in section 13.1.1 are not enforced in review. |
| Evidence | Section 8 considerations 3 and 5, D-002, FR-013, FR-019, section 5’s cost constraint, and the business needs in section 1.1. Assignment 2 Task 3, sections 4.2 and 4.3. |
| Later consequence | Influences the repository structure, component names, deployment and the layering, the D-012 authentication approach, and the interface documentation in section 13.6. Because the business logic sits in services, adding a JSON API later is additive rather than a rewrite. |
| Superseded version | 20/09/2026: option C, a React SPA over a Laravel JSON API, was the first selection. It was replaced by option B through CR-017 after the section 13.3 matrix ranked B-009 highest and the SPA’s network boundary, CORS handling and second deployable were found to add cost with no requirement that needed them. The SPA analysis is kept as option C in section 13.1.2. |

D-007: Technology stack selection

| Field | Record |
| --- | --- |
| Status | New at M2; closes D-004 |
| Context | The technology stack had to be selected on evidence before construction begins. Section 13.3 scored nine common web bundles against ten weighted criteria drawn from Master Brief section 18.1. |
| Constraints | Free or low-cost services (CON-003); a three-person team with PHP new to all members and React/TypeScript known to two of the three (CON-006); tools must run on the BC Desktop or team laptops (CON-007); the fixed milestone schedule (CON-002). |
| Alternatives | Nine bundles, B-001 to B-009 (section 13.3.1). MERN was excluded before scoring because MongoDB is not relational. The PERN variant was scored as B-001. Leading scores: B-009 Laravel with Inertia 85%, B-003 Laravel with Blade 83%, B-005 Django 82%, B-006 ASP.NET Core with Razor 80%, B-004 Laravel API with a separate SPA 74%. |
| Decision | Adopt bundle B-009: Laravel (PHP) with Inertia serving React and TypeScript components, over PostgreSQL. This is the highest-scoring bundle in the section 13.3.3 matrix and is consistent with the architecture selected in D-006. |
| Rationale | B-009 scores highest on the criteria carrying the most weight. It deploys as a single unit, which gives the team a working deployment quickly, and CivicConnect has no requirement to scale the presentation layer independently of the application. It keeps session-based security and framework validation, and it uses the React and TypeScript that two members already work in while the team takes on Laravel. PostgreSQL wins its own sub-matrix at 96% on CHECK constraints, composite foreign keys and transactional DDL, which the D-008 and D-015 integrity design depends on. Tiebreakers between the four candidates within five percentage points: (1) reuse of the React and TypeScript skills two members already have (2) a single deployable with session authentication (3) an officially supported Laravel starter kit for React, Inertia and TypeScript (4) PostgreSQL integrity support. B-009 is the only candidate that meets all four |
| Trade-offs | PHP is new to all three members, so the framework learning curve is real and is the weakest dimension of every Laravel bundle. Inertia couples the front-end and back-end: page props are not a reusable API contract. |
| Risks | R-001 learning curve; R-014 toolchain availability on the BC Desktop, not yet verified; R-015 no proof of concept before M3. |
| Evidence | Section 13.3.3 weighted matrix; section 13.3.4 database sub-matrix; section 13.3.5 result and sensitivity check; Assignment 2 Task 3; the laravel/react-starter-kit repository (Laravel, React, Inertia, TypeScript) as evidence that this combination is an officially supported path. |
| Later consequence | If velocity targets are missed at the M3 checkpoint, the fallback recorded against R-001 is B-003, the same Laravel backend with Blade views, which replaces only the presentation layer. Target versions and compatibility assumptions are recorded in section 13.3.6 and confirmed against composer.lock and package.json when the project is created. |

D-008: Status change and audit write in a single transaction

| Field | Record |
| --- | --- |
| Status | New at M2 |
| Context | D-002 (Milestone 1) committed CivicConnect to recording every status change as an immutable history entry, but left the transactional and concurrency detail open. That detail has to be settled before the persistence layer is built. |
| Constraints | Free-tier relational database (Section 5). FR-018 (only the assigned staff member may update a request). NFR-003 (user and timestamp on every status change). Three-person team and academic schedule. |
| Alternatives | (a) Single relational transaction, application-managed, with optimistic concurrency via a version column and a service-layer validation check backed by a database constraint. (b) Outbox/event-sourced write, where the status change and a separate outbox event are written atomically and a worker process later handles downstream effects. |
| Decision | Adopt (a). RequestStatusService::transition() updates service_requests.status guarded by an optimistic version check (a stale version raises StaleRequestException, which the controller turns into a redirect back with an error message) and inserts the matching request_status_history row, both inside one DB::transaction call. |
| Rationale | Option (a) delivers exactly the atomicity D-002 requires without introducing a worker process, message queue or eventual consistency the team does not yet have a justified need for. It maps onto Laravel’s DB::transaction(). Laravel has no built-in optimistic locking, so the version check is written explicitly: the update includes WHERE id = ? AND version = ?, increments version, and if no row is affected RequestStatusService throws StaleRequestException. |
| Trade-offs | The transaction briefly holds a database connection open. Calling code has to catch a version conflict and retry or surface it to the user rather than assuming every write succeeds. |
| Risks | The database CHECK constraint on status and the database transition table (request_status_transitions) have to be kept in sync by hand until an automated consistency check exists (Forward Engineering Consideration #3). Concurrent staff edits are tracked as R-008. |
| Evidence | Assignment 2, Task 2, Sections 3.2 to 3.4. |
| Later consequence | [to be updated once Milestone 3 implementation and test evidence is available] |

D-009: Splitting status-change side effects

| Field | Record |
| --- | --- |
| Status | New at M2; adapts the Assignment 2 recommendation |
| Context | FR-016 and FR-019 require an audit entry recording who changed a request’s status and when. FR-007 requires the requester to see the update reflected on their side. Forward Engineering Consideration #3 flags that the audit trail has to be designed in from the outset rather than retrofitted. |
| Constraints | The audit write must stay inside the D-008 transaction so it can never be silently skipped. A notification failure must not roll back the status change. Laravel’s event/listener mechanism changes what building this reaction costs compared with the Assignment 2 research. |
| Alternatives | (a) A general-purpose Observer applied directly at the ServiceRequest entity, as Assignment 2 Task 1 recommended, with the audit write as one of the registered observers. (b) Split the two reactions: audit write synchronous inside the D-008 transaction, every other reaction a queued listener on a RequestStatusChanged event dispatched only after commit. (c) A general-purpose domain-event/pub-sub dispatcher. |
| Decision | Adopt (b). The audit write is written directly inside RequestStatusService::transition() as part of D-008. NotifyRequesterOfStatusChange is a queued listener (implements ShouldQueue) on the RequestStatusChanged event, dispatched once the transaction commits. RequestStatusChanged implements ShouldDispatchAfterCommit, so Laravel dispatches it only after the D-008 transaction commits; if the transaction rolls back, the event is never dispatched |
| Rationale | Assignment 2 Task 1 recommended a uniform Observer over a full dispatcher because a dispatcher looked like more infrastructure than a single entity raising events needed. That reasoning changes once Laravel is the confirmed stack: the event/listener mechanism already exists. What Assignment 2 Task 1 did not consider is Assignment 2 Task 2’s constraint that the audit write must be inside the same transaction as the status update, so a uniform after-commit Observer would not fit. Splitting the reactions keeps D-008’s atomicity guarantee intact. |
| Trade-offs | The status-change reaction logic is no longer handled by one uniform mechanism, which is one more thing to explain in the defence. A misconfigured listener still silently skips its reaction. |
| Risks | If a future reaction is added as a queued listener without checking whether it also needs to be inside the transaction, it could reintroduce a consistency gap. |
| Evidence | Assignment 2, Task 1, Section 2.1 (Design Problem 1). Assignment 2, Task 2, Sections 3.2 to 3.4. |
| Later consequence | [to be updated once Milestone 3 implementation and test evidence is available] |

D-010: Category-specific handling

| Field | Record |
| --- | --- |
| Status | New at M2 |
| Context | D-001 fixed the category vocabulary itself, but not how category-specific validation and routing behaviour is implemented. Writing that behaviour as one long conditional means every new category requires editing and retesting the same method. |
| Constraints | Adding a category should not require editing already-tested code. CivicConnect’s categories differ in behaviour, not only in the fields they require. |
| Alternatives | (a) Strategy pattern, one handler class per category behind a shared interface. (b) Factory Method producing category-specific request objects. (c) A configuration-only lookup of required fields. |
| Decision | Adopt (a), the Strategy pattern, as Assignment 2 recommended. Each category implements a shared CategoryHandler interface (rules(), defaultAssignee()). CategoryRegistry, bound in AppServiceProvider, resolves the handler for a given category code, and an unrecognised code falls back to OtherHandler. StoreServiceRequest merges the resolved handler’s rules into its own FormRequest validation. |
| Rationale | The configuration-only approach was set aside because the categories differ in behaviour, not only in required fields. Factory Method was set aside because the categories differ in behaviour, not in data shape; a subclass per category would force a class hierarchy onto the persisted request and complicate the data model (Assignment 2, Task 1). With Strategy, adding a category means one new handler class, one seeded category row and one line in the CategoryRegistry mapping; existing handlers and StoreServiceRequest are not edited. |
| Trade-offs | Requires a small registry/lookup mechanism. If the category list stays very small with simple, near-identical rules, this is more structure than the problem needs. |
| Risks | If the handler set drifts from the seeded category list, a request could silently resolve to OtherHandler (linked to Risk R-007). |
| Evidence | Assignment 2, Task 1, Design Problem 2. Section 13.4.2. |
| Later consequence | [to be updated once Milestone 3 implementation and test evidence is available] |

D-011: Status-to-notification integration mechanism

| Field | Record |
| --- | --- |
| Status | New at M2 |
| Context | The status-update component and the notification component must exchange information without a notification failure affecting the status change (Assignment 2 Task 3). |
| Constraints | A notification failure may not roll back a status change. No network boundary without justification. Free-tier hosting with no Redis instance available. |
| Alternatives | (a) Synchronous in-process call. (b) Asynchronous in-process event handled by a queued listener. (c) A separate notification service called over HTTP/REST. |
| Decision | Adopt (b), as Assignment 2 recommended: a queued listener on the RequestStatusChanged event, using the database queue driver so the queue lives in PostgreSQL. |
| Rationale | Option (a) lets a mail-provider failure roll back the transaction, the exact failure Task 3 identified. Option (c) adds a second deployable, a security boundary and a versioned contract for benefits, such as independent scaling and third-party consumers, that this project does not need. Option (b) satisfies both constraints inside the single deployable chosen in D-006. |
| Trade-offs | Requires a queue worker process in every deployed environment. Delivery is eventual rather than immediate. |
| Risks | R-009: a free-tier host without background-worker support would accept notifications that are never sent. |
| Evidence | Assignment 2, Task 3, Sections 4.2 and 4.3. Section 13.7.3. |
| Later consequence | Makes a persistent worker process a hosting requirement, which constrains D-013. The email provider is recorded in section 13.7 once a free-tier provider is confirmed. |

D-012: Authentication and role-based access control

| Field | Record |
| --- | --- |
| Status | New at M2 |
| Context | FR-010, FR-011 and FR-018 require role-based access. NFR-002 requires authorisation on every read. Forward Engineering Consideration #1 warns that retrofitting access control forces rework of the data model and UI. |
| Constraints | Sensitive request categories (Forward Engineering Consideration #6). Credentials hashed at cost factor 12 (NFR-001). A single deployable with server-side rendering through Inertia (D-006). |
| Alternatives | (a) Laravel’s session-based authentication with CSRF protection and framework policies. (b) API tokens held in browser storage. (c) An external identity provider. |
| Decision | Adopt (a): session cookie authentication with CSRF protection, and authorisation enforced by ServiceRequestPolicy at the data-access layer rather than per screen. Roles are stored on users.role. |
| Rationale | Because D-006 keeps one deployable and Inertia requests are ordinary authenticated requests, no cross-origin token exchange is needed, which removes the CORS and stateful-domain configuration a separate SPA would have required. Framework policies apply the same rule to every query path, which is what NFR-002 and ASR-002 require. An external provider adds cost and an external dependency for no stated requirement. |
| Trade-offs | Session authentication assumes browser clients. A future non-browser client would need token authentication added alongside. |
| Risks | The role model must match the data model, CR-009 fixed it at three roles. Policy coverage must be verified by test rather than assumed. |
| Evidence | FR-010, FR-011, FR-018, NFR-001, NFR-002. Section 13.5.1. |
| Later consequence | Determines the users.role column, the policy test set for M3, and the route-level role guards, which remain a usability convenience only. |

D-013: Deployment direction and environment strategy

| Field | Record |
| --- | --- |
| Status | New at M2; supersedes D-005. Closed by decision 16. |
| Context | A deployment direction is needed so the architecture and technology choices can be checked for plausibility, but provider selection depends on evidence the team does not yet have. |
| Constraints | Free or low-cost services (CON-003). One web process, one queue worker and one PostgreSQL instance (ASR-006). Environment separation (Master Brief section 17). A persistent worker is required by D-011. |
| Alternatives | (a) Commit to a named provider now. (b) Fix the topology and environment strategy and defer the provider. (c) Defer the whole question to M3. |
| Decision | Adopt (b). The topology is one Laravel deployable serving Inertia pages and compiled assets, one queue worker sharing that codebase, and a managed PostgreSQL instance. Development runs on Docker Compose and test runs in CI against a PostgreSQL service container. The specific provider is deferred. |
| Rationale | Because D-006 produces a single deployable, no separate static host is required, which widens the range of usable free tiers and shortens the deployment path. Fixing the topology is enough to size free-tier limits and validate the architecture, whereas naming a provider before verifying worker support and backups would be an unevidenced claim. |
| Trade-offs | Environment-specific configuration and secrets handling must be designed before the provider is known. |
| Risks | R-009 worker support on free tiers. R-013 idle pausing and storage caps. NFR-006 recovery depends on the provider’s backup facility. |
| Evidence | Sections 13.7.1 to 13.7.5. Master Brief section 17. Free-tier limits recorded in section 13.7.4. |
| Later consequence | Provider selection remains open in section 13.8 and must be closed before the M3 staging deployment. |

D-014: Construction deferred to Milestone 3

| Field | Record |
| --- | --- |
| Status | New at M2 |
| Context | Milestone 2 is a design baseline for this team, and construction is planned to begin in Milestone 3. |
| Constraints | The fixed M2 window (CON-002). PHP is new to all three members (CON-006). Milestone 2 brief section 7 expects development to have begun. |
| Alternatives | (a) Build a thin vertical slice during M2. (b) A throwaway prototype only. (c) Defer construction to M3 with the repository, CI and backlog prepared during M2. |
| Decision | Adopt (c): the design baseline, backlog and repository governance (protected main and two-reviewer approval) are prepared during M2. The repository folder structure, README, pull request template and CI workflow are created at the start of M3 together with the Laravel project, and application code begins in M3. |
| Rationale | Concentrating construction in M3 keeps the M2 evidence coherent and avoids partly-built code that contradicts the baseline. The team accepts that the evidence for the development criterion is correspondingly limited. |
| Trade-offs | Implementation and verification columns in the RTM read ‘Planned - M3’, and the end-to-end trace is complete only as far as the technology decision. |
| Risks | R-015: without a proof of concept, the stack and toolchain risks (R-001, R-014) remain unvalidated until M3. |
| Evidence | Milestone 2 brief sections 5.7, 7 and 12. RTM section 6.2 status values. Forward Engineering Consideration #7. |
| Later consequence | Sets the M3 build order: the first deliverable is a vertical slice covering FR-001, FR-017 and FR-019. |

D-015: Status taxonomy and controlled transitions

| Field | Record |
| --- | --- |
| Status | New at M2; closes Forward Engineering Consideration #2 |
| Context | Forward Engineering Consideration #2 left the status vocabulary open, but FR-006, FR-017, FR-019 and the D-008 transaction all depend on a fixed set of states and legal transitions. |
| Constraints | Status updates limited to pre-defined options (FR-017). Transitions must be auditable (D-002) and enforceable in the database (D-008). |
| Alternatives | (a) Free-form status text. (b) A fixed enumeration checked in application code only. (c) A fixed enumeration plus a seeded transition table referenced by the history rows. |
| Decision | Adopt (c): the statuses are open, assigned, in_progress, resolved and closed, with legal transitions seeded in request_status_transitions and referenced by a composite foreign key from request_status_history. |
| Rationale | The service layer can return a clear message for an illegal transition while the database refuses it as a backstop, which is the layered validation Assignment 2 Task 2 recommended. A code-only enumeration leaves the database able to store states the business rules forbid. |
| Trade-offs | Adding or renaming a status requires a migration and a seeded row rather than a code change alone. |
| Risks | If the CHECK constraint and the transition table drift apart, a legal transition could be rejected or an illegal one accepted (Forward Engineering Consideration #3). |
| Evidence | Assignment 2, Task 2, Section 3.2. Forward Engineering Consideration #2. Change record CR-010. |
| Later consequence | Fixes the status options offered in the UI, the transition test set for M3, and the definitions of open and overdue used in reporting. |

D-016: Database Provider selection

| Field | Record |
| --- | --- |
| Status | New at M3 |
| Context | A database provider was required to host the database. |
| Constraints | The database provider must be a free-tier service |
| Alternatives | Supabase |
| Decision | Make use of the provider NEON to host the database for staging and production. |
| Rationale | The free plan provides 1GB storage, hosts PostgreSQL 18 which we are using, and allows different branches for staging and production |
| Trade-offs | Suspends after 5 minutes of being idle, and a point-in-time restore on the free plan remains unclear. |
| Risks | R-002, R-013 |
| Evidence | 53 tests run and passed on the NEON staging database. |
| Later consequence | AWS London being the nearest causes a latency of 150 to 200 ms, meaning NFR-004 will be at risk. The free tier does have the limits of 100 computing hours and 1 GB storage per project., reducing scalability. |

D-017: Application deployment environment

| Field | Record |
| --- | --- |
| Status | New at M3 |
| Context | The hosting provider for the application has been deferred. The database hosting provider has been decided on and tested. |
| Constraints | Free or low-cost services (CON-003). The M3 schedule (CON-002). The host must support a persistent queue worker and the scheduler (D-011, AS-001, R-009) |
| Alternatives | (a) Choose a host now and deploy the stating app during milestone 3. (b) Run the application locally for milestone 3, but connect to the staging database on Neon. (c) Run everything locally. |
| Decision | Adopt (b) |
| Rationale | The staging database has already been set up, but there is no decision yet for where the application will be hosted. Milestone 3 aim currently for a MVP. Decision (a) would divert attention away from the construction of the application itself, risking functionality. Decision (c) would leave the hosted database untested. |
| Trade-offs | No public staging URL for milestone 3, and hosting specific problems can occur during Milestone 4. |
| Risks | R-009 (worker support), R-010 (session/APP_URL configuration), R-013. AS-001 stays unverified until M4. |
| Evidence | Neon staging results as of section 13.2.6. Milestone 3 brief allows for a simulated staging environment. |
| Later consequence | OD-01’s application-host part stays open until M4. OD-02 (email/SMS) is decided together with the host. |

D-018: Chosen Application deployment environment

| Field | Record |
| --- | --- |
| Status | New at M3, Supersedes D-017 |
| Context | D-017 was originally deferred to milestone 4. However, due to the postponement of the Milestone 3 submission and milestone 4 not being extended as well, the hosting service for the application has been moved back to milestone 3. |
| Constraints | Free services (CON-003). The M3 schedule (CON-002). The app must reach the Neon database over SSL (D-016). D-011 expects a queue worker and a scheduler (AS-001, R-009) |
| Alternatives | (a) Render free web service. (b) AWS Free plan in London. (c) Koyeb free web service. (d) Oracle Cloud Always Free server. |
| Decision | Chosen option (a). The host for the application will be Render’s free tier, built from a Docker image in the Frankfurt region. The hosted application shall connect to the database hosted on NEON. |
| Rationale | Render has a free-tier option and gives the team a public staging URL with the least setup. (b) runs a worker and a scheduler properly, but does not have free-tier service. (c) requires card information to make use of the service, and has a smaller CPU capacity. (d)needs the highest level of server administration among the alternatives while also having know capacity issues. |
| Trade-offs | The app sleeps after 15 minutes without traffic and takes around a minute to warm up again. There are no free background workers, meaning the email delivery will be done during the web request. It has a limited RAM capacity at 512MB, and the file system is reset on each deployment. |
| Risks | R-009 (worker support): mitigated by synchronous mail and GitHub Actions. R-010 (APP_URL/session). R-013. AS-001 is answered as not met on this host, and the mitigation replaces it.. |
| Evidence | Flavio Copes (Copes, 2026) compared 11 hosting providers’ free tier services. Deployed 16/10/2026 to https://civicconnect-staging-kski.onrender.com; health check /up returned 200, migrations reported nothing to migrate, and a status-change email was delivered. |
| Later consequence | Closes the application-host part of OD-01. If the project needs queued notifications or a host that is always on, the plan changes to Render’s paid tier or option (b). OD-02 (email) has to use a provider that works with synchronous sending. |

D-019: Emailing service

| Field | Record |
| --- | --- |
| Status | New at M3. Closes OD-02. |
| Context | FR-007 and CR-011 require an email when a request's status changes. |
| Constraints | D-018 hosts the app on Render's free tier, which has blocked outbound SMTP ports since September 2026, making ordinary SMTP sending no longer possible |
| Alternatives | (a) Resend, through its HTTPS API. (b) Brevo, through its HTTPS API. (c) SMTP through a Gmail or Outlook mailbox. (d) Mailgun or Mailtrap. |
| Decision | Chosen (a). Laravel’s built-in resend mail driver is used, sending emails form onboarding@resend.dev. On staging a code line was added (MAIL_DEMO_TO) in order to redirect all emails to a demo inbox, as the seeded users does not actually exist. |
| Rationale | Resend has a built-in Laravel driver, so no custom code is needed. It uses HTTPS, so Render's SMTP block does not affect it. Its sender address is authenticated by Resend, which lowers the junk-mail risk compared with Brevo sending as a campus address. (c) is blocked by Render. (d) needs a verified domain. The call is outbound and server-to-server, and the key is held in environment variables, so the browser never sees it. This is consistent with D-006 and D-012, because CivicConnect still exposes no API of its own. |
| Trade-offs | Without a verified domain, Resend only delivers to the account owner's address, so the demo can only email one inbox. Free limits are 100 emails per day and 3,000 per month. |
| Risks | R-009 (sending during the web request adds delay, and there is no automatic retry). AS-004 is answered: the free limit is enough for the demonstration. |
| Evidence | 15/10/2026: a test email from the local application, addressed to the seeded user thandi.nkosi@example.com, was redirected by MAIL_DEMO_TO and delivered to the demo inbox. |
| Later consequence | Production will require a verified domain, and the code sniper (MAIL_DEMO_TO) must be removed |

D-020: offer/decline rule

| Field | Record |
| --- | --- |
| Status | New at M3. Answers the open point in FR-015 on what happens after a declined offer. |
| Context | FR-015 lets staff and management offer a request to a staff member, who accepts or declines it. FR-015 did not say what happens after a decline, so a request could keep waiting for someone to accept it. |
| Constraints | Render’s free tier runs no worker or scheduler (D-018), so the rule must work at the moment someone answers, without timed jobs. Every offer, decline and acceptance must be recorded (FR-016). |
| Alternatives | (a) Allow 3 declines per calendar month; after that the next offer is accepted automatically. (b) Keep the offer pending but remove Decline once the limit is reached. (c) Unlimited declines; the request returns to the open pool after each decline. (d) Offers expire after a set time. |
| Decision | Chosen (a). A staff member can decline up to 3 offers per calendar month; after that their next offer is accepted automatically. A declined offer moves to the staff member with the fewest open requests (then lowest id), skipping anyone who already declined this request and the person who made the offer. If nobody is left, the request returns to the open pool. Take is blocked while an offer is pending. Staff and management can make offers; requestors cannot. |
| Rationale | An offer can never get stuck: it is accepted, passed to the next person, or returned to the open pool. No scheduled job is needed, which option (d) would require and Render’s free tier cannot run (D-018). Passing the offer to the person with the fewest open requests spreads the work. |
| Trade-offs | An automatic accept assigns work the staff member never actively accepted. The count resets each calendar month, so 3 declines on 31 October and 3 more on 1 November are possible. The next person is chosen by workload, not by skill or category. |
| Risks | R-008 (two staff acting on the same request): the request and offer rows are locked while an answer is saved, and each decline locks the staff member’s row so two declines at once cannot pass the limit. SQLite ignores these locks, so this is only protected on PostgreSQL (TD-03). |
| Evidence | Implemented in OfferService and RequestAssignmentController, merged in PR #24 (ee33a95). tests/Feature/OfferTest.php (15 tests) covers the decline limit at 2 and 3 declines, automatic accept, declines from last month not counting, passing the offer to the next person, the return to the open pool, Take blocked during an offer, and that only the offered person can answer. |
| Later consequence | FR-015’s acceptance criteria are extended through CR-032. A later version could choose the next person by category or skill instead of workload. |

# 10. GitHub & Team Governance

## 10.1 Repository

| Control | Status / Evidence Location |
| --- | --- |
| Repository URL | https://github.com/Destroyer1819/SEN381_Project |
| Main branch protected | Yes |
| PR required for substantive changes | Yes |
| Minimum two-reviewer approval configured | Yes |
| Self-approval disabled | Yes |
| Secrets and credentials policy | .gitignore excludes environment files; no credentials are committed; environment values are documented in .env.example; CI secrets will be held in GitHub Actions secrets once the CI workflow exists. |
| Issue board / backlog in use | https://github.com/users/Destroyer1819/projects/2 |
| Pull request template | planned |
| Continuous integration workflow | In place: .github/workflows/tests.yml |
| Required status checks on main | Not configured; merges wait for a green CI run by team rule |

## 10.2 Team Working Agreement

Roles: All three members contribute across requirements, engineering artefacts and repository work. No member is confined to a single artefact type. Current section ownership: Jared - Sections 1, 2 and 3 (Problem/Business Need, Stakeholder Analysis, Scope Baseline), Michael - Sections 4 & 6 (Requirements, RTM), Xander - Sections 5, 7, 8, 9, and 10 (Constraints, Risk Register, Forward Engineering Considerations, Decision Log, GitHub Governance). Ownership may shift for M2 to M4 as the work changes.

Communication: The team will check in at least twice a week (in person or via chat) and immediately before each milestone deadline. Blockers are raised as soon as identified rather than at the next scheduled check-in.

Commit & PR conventions: Commits use short, meaningful messages describing the change (e.g. "Add NFR-004 performance requirement"). Substantive changes to controlled artefacts (PED sections, registers, code) go through a Pull Request. Direct pushes to main are not used for substantive change, per the Master Project Brief section 9.

Review: Every PR requires review from the two team members who did not author it before merging. Reviewers check alignment with requirements/acceptance criteria, consistency with other PED sections, and flag anything that looks rubber-stamped rather than genuinely reviewed.

Conflict resolution: Disagreements on content or approach are raised in the team chat first. If unresolved within 24 hours, the team discusses it together (in person or on a call) rather than letting it stall a PR. The lecturer is consulted only if the team genuinely cannot reach agreement.

AI use: Any material AI-assisted contribution must be logged in the AI Usage Register (Section 11) by the student who used it, including what was verified, changed or rejected, before it is merged into a controlled artefact.

## 10.3 Repository structure and continuous integration

The repository is organised so that documentation, decisions and code sit beside each other and a single pull request can carry a change to all three.

| Path | Contents |
| --- | --- |
| docs/PED/ | The Project Engineering Document |
| docs/decisions/ | One file per decision record, D-001 onward |
| docs/requirements/, risk/, change/ | Requirement notes, risk working papers, change request forms |
| docs/architecture/, deployment/ | Diagrams and environment notes |
| app/, database/, resources/js/ | Laravel application code, migrations and React components (from Milestone 3) |
| tests/ | Feature and unit tests (from Milestone 3) |
| .github/workflows/ | Continuous integration workflow |
| .github/pull_request_template.md | Pull request template |

This structure will be created at the start of Milestone 3 together with the Laravel project (D-014).

# 11. AI Usage Register

| Date | Student | Tool | Engineering Task | AI Contribution | Verification | Decision | Issues Found |
| --- | --- | --- | --- | --- | --- | --- | --- |
| 08/09/2026 | Michael | Claude | Finding sources | Provided a list of sources | Read the sources | Accepted | None |
| 08/09/2026 | Michael | Claude | Understanding the project | Provided explanations | See if the explanation makes sense, and check with other online sources | Partially accepted | Not all of the explanations were relevant to the project |
| 07/09/2026 | Xander | Claude | Drafting M1 PED template structure (all section headings, tables, guidance notes) | Generated the section structure, table layouts and instructional notes matching the M1 brief's required outputs | Checked every table's required fields against the Milestone 1 Brief section 3 and Master Brief sections 9-13 field-by-field | Accepted (structure only, no project content yet) | None. structure only, no factual claims to verify |
| 08/09/2026 | Xander | Claude | Drafting Sections 5 (Constraints), 7 (Risk Register), 8 (Forward Engineering Considerations) and 9 (Decision Log) content | Drafted CivicConnect-specific constraint implications, 7 project risks, 6 forward-engineering concerns and 5 decision-log entries | Cross-checked every claim against the CivicConnect Master Project Brief and Milestone 1 Brief sections cited inline (e.g. section 2, 3, 9, 18.1); reviewed with Michael before merging | Partially accepted | Owner names were placeholders ([Name]) and needed real assignment; some risk/decision wording needed personalising against the team's actual scope once agreed |
| 09/09/2026 | Xander | Claude | Reviewing merged team document (Michael's Sections 4 & 6) for consistency and completing AI Usage Register / Risk Register owners / Team Working Agreement | Identified that AI Usage Register did not yet log Xander's own AI-assisted sections; drafted Section 10.2 Team Working Agreement content; proposed a draft Risk Register owner distribution; aligned FR-001 wording between Section 4 and the RTM | Reviewed against the Master Project Brief's Responsible AI standard (section 10) requiring every material AI contribution to be logged and verified; owner assignments and working-agreement content flagged to team as draft, pending confirmation | Accepted, pending team confirmation of owner assignments | None found, flagged as draft/pending team sign-off rather than a factual error |
| 04/09/2026 | Michael | Claude | Linking of multiple sections, such as the ASR’s to the influence of the ASR’s on the stakeholders. | Found potential links and provided explanations | Read through the explanations, and verified if the links found are valid | Partially accepted | Some potential links included links with little in common to what they are linked with. |
| 24/09/2026 | Jared | Claude | Structuring the Milestone 2 work: what evolves in the PED and where each M2 deliverable belongs | Produced a section-by-section plan mapping M2 brief and Master Brief requirements to PED sections | Checked each mapping against the Milestone 2 brief sections 4, 5 and 12 and the Master Brief section 20.2 list | Accepted with changes | The first version proposed new sections for everything; the team required the M1 baseline to be extended instead |
| 25/09/2026 | Jared | Claude | Technology selection research and the weighted matrix structure | Listed common web bundles, proposed criteria and weights traced to constraints and ASRs, and produced illustrative scores | Team scored every cell itself and rejected the initial weighting; free-tier and licensing claims checked against the providers’ own pricing pages | Partially accepted | Early scoring treated capability as one criterion and had to be split into language familiarity and framework learning; a lock-in score was inconsistent and was corrected |
| 26/09/2026 | Xander | Claude | Drafting decision records D-007 and D-010 to D-015, and restructuring Section 9 | Drafted the missing decision records in the Master Brief section 13 field structure and reformatted the log one decision per table | Each record checked against the Assignment 2 task it cites and against the design in Section 13; D-006 and D-007 rewritten by the team after the Inertia decision | Accepted with changes | The first draft recorded the SPA architecture, which contradicted the matrix result and was corrected |
| 26/09/2026 | Xander | Claude | Raising risks R-008 to R-016 and reviewing R-001 to R-007 | Proposed new risks traced to the M2 decisions, and Milestone 2 review notes for the existing risks | Team confirmed or changed every probability, impact and owner; R-010 reworded because Inertia removed the CORS exposure | Accepted with changes | Suggested owners and ratings were placeholders and were reassigned by the team |
| 26/09/2026 | Jared | Claude | Consistency review of the merged document | Identified contradictions and missing cross-references between Sections 6, 8, 9, 11, 12 and 13 | Every reported issue checked in the document before acting on it | Partially accepted | Some reported items were formatting artefacts of the conversion rather than real defects |
| 04/10/2026 | Michael | Claude | Database hosting research | Compared free PostgreSQL hosts | Checked providers’ docs and pricing pages to see if it conforms to the constraints | Accepted (Neon, London) | None |
| 05-06 /10/2026 | Michael | Claude | Database Schema review | Reviewed types, checks, foreign keys and delete rules against the ERD | Reviewed pgAdmin backups after each change | Accepted | Some relational and datatype errors in the database found during review, and resolved. |
| 10/10/2026 | Michael | Claude | Schema check | Wrote 53 tests | Requested explanations behind the logic of each test, and compared this to the tests and their outcomes | Accepted | None |
| 10/10/2026 | Michael | Claude | Dummy data generation | Created the dummy data | Schema enforcement should have caught illegal statements. Checked if statuses are valid between the requests and the change history. | Partially accepted | Password hashing was initially incorrect, as it was hashed only 10 times instead of the required 12. New passwords were generated. |
| 11/10/2026 | Jared | Claude | Learing PHP | Explained how to code in PHP | Used the explanation to code the application. Code worked | Accepted | None |
| 15/10/2026 | Michael | Claude | Research free tier hosting services | Found sources for comparing different free tier hosting services | Personall inspection of the sources and manual comparison between services. | Accepted | None |
| 15/10/2026 | Micahel | Claude | Research free tier emailing services | Found sources for comparing different free tier emailing services that will work with the hosting services | Personall inspection of the sources and manual comparison between services. Did a test run, and a test email was successfully sent. | Accepted | None |
| 15/10/2026 | Jared | Claude | Fixes for Xanders branch | Fixed an issue where Xanders branch was outdated | Had to make sure what it deleted was unused UI files | Accepted | None |
| 16/10/2026 | Jared | Claude | Test case creation | Drafted ideas for tests | Manual inspection of tests | Accepted | None |
| 16/10/2026 | Xander | Claude | Creation of the sort control, average resolution card, and 403 and 404 screens. | Wrote drafts for these tasks | Maunual inspection of the created sort control, resolution card, and the 403/404 screens. | Accepted | None so far. |
| 16/10/2026 | Michael | Claude | Sections 14-16 | Found the links between sections | Inspected each link and verified if these links are valid and sensible | Accepted | None. |

# 12. Baseline Readiness Checklist

## Milestone 1 Readiness Checklist

- PED v1.0 is complete, coherent, versioned and reviewed

- Scope and requirements are baselined rather than merely drafted

- RTM, Risk Register, Decision Log, Forward Engineering Considerations and AI Usage Register are current

- GitHub governance required by the Master Project Brief is demonstrable

- Team Working Agreement is agreed and controlled

- Baseline sign-off/gate evidence is ready

- All students can independently locate and explain the project foundation and its Software Engineering significance

- All students are prepared to present professionally and defend the team's evidence individually

## Milestone 2 Readiness Checklist

- PED v2.0 visibly continues M1 and retains traceable history - Met: document control, change record CR-001 to CR-019.

- RTM has evolved with architecture/data/design/interface/technology/implementation/verification/status evidence - Met: Section 6.2 (implementation and verification Planned M3 under D-014).

- Risk Register, assumptions/dependencies and Forward Engineering Considerations reflect new evidence - Met: Sections 7, 5.2 and 8.

- ASRs/quality drivers are project-specific and linked to architecture decisions - Met: Section 4.3.

- Architecture selection and diagrams are defensible and proportionate - Met: Section 13.1, D-006, CR-017.

- Data/persistence decisions are documented and linked to correctness/quality needs - Met: Section 13.2, D-008, D-015.

- Technology stack is justified with evidence rather than preference - Met: Section 13.3, D-007.

- At least two genuine design problems have final pattern/approach decisions informed by A2 research - Met: Section 13.4, D-009, D-010.

- A2 research is referenced as supporting evidence, not copied - Met: D-008 to D-011.

- Initial interface/integration decisions are documented where applicable - Met: Section 13.6.

- Architecture, Technology & Initial Design Baseline is identifiable and controlled - Met once signed: Baseline Approval (Milestone 2).

- Meaningful development has begun against the baseline - Deferred to Milestone 3 by D-014.

- Application/technical documentation matches the repository/application - Deferred with D-014.

- At least one requirement traces into implementation and verification evidence - Trace complete to the technology decision (D-007); implementation and verification planned in M3 (D-014).

- GitHub history demonstrates progressive controlled work and peer review - Met for documentation: pull requests with two approvals.

- Relevant A2 SCM/CI recommendations are adopted progressively - Partly met: protected main and two-reviewer approval adopted; PR template and CI at the start of M3.

- AI use is recorded and verified - Met: Section 11.

- Every team member can defend the shared evidence - confirmed

# 13. Solution Design Baseline

## 13.1 Architecture

## 13.1.1 Logical components

| Component | Responsibility |
| --- | --- |
| Submission | Accepting, validating, and providing persistence to the new requests that are being made. |
| StatusAudit | Status changes, updates and appending the records of who made a change, what change was made, and when was the change made. |
| Assignment | Responsible for the ownership of a request, be it assigning a request, offering a request to another staff member, or accepting an offered request. |
| RequestQuery | Reading and then returning of data. Includes search functions, sorting, filtering, listing and pagination of data. |
| Authentication | Verifies who the user is (session login) and which of the three roles they hold (D-012). |
| Category handling | Category specific validation and routing rules. |
| Notification | Delivering notifications about the status changes to the requesters. |
| Retention | Enforcement of the 5-year retention before permanent deletion rules. |
| Authorisation | ServiceRequestPolicy: decides which requests each role may see and change, applied on every query path. |
| Reporting | On-demand management reports: counts by status and category, the overdue list and average time to resolution. |

## 13.1.2 Considered alternatives

| Option | Description | ASRs supported | Risks / weaknesses | Decision |
| --- | --- | --- | --- | --- |
| A. Server-rendered monolith (Blade) | Pages are rendered by Laravel Blade views and the browser submits ordinary forms. No client-side application. | ASR-001, ASR-002 (authorisation stays on the server), ASR-006 (single deployable). | Leaves the team’s React and TypeScript experience unused; less interactive filtering and status updates. | Rejected - kept as fallback B-003 (R-001) |
| B. Layered modular monolith with Inertia-rendered React | Laravel controllers return Inertia responses and React + TypeScript components render the pages. One deployable, session authentication, no JSON API. | ASR-002 (policies on every query path), ASR-003 (D-008 transaction in one process), ASR-004 (business rules in services), ASR-006 (one web process, one worker, one database). | Front-end and back-end are coupled and released together; page props are not a reusable API (R-016). | Selected (CR-017) |
| C. Layered modular monolith with a separate React SPA over a Laravel JSON API | A React single-page application calls a Laravel API using token or cookie-based authentication. | ASR-002, ASR-003, ASR-004. | Adds a network boundary, CORS and token handling, a second deployable and duplicated validation for a client the project does not need to serve independently (Assignment 2, Task 3). | First selected; superseded by CR-017 |
| D. Distributed services | Separate deployables for requests, notifications, reporting and identity. | None better supported than option B. | The status change and audit write become a distributed transaction (ASR-002, ASR-003); several deployables exceed free-tier limits (ASR-006). | Rejected |

## 13.1.3 Justification of selected architecture

CivicConnect adopts option B: a layered modular monolith in which Laravel controllers return Inertia responses and React with TypeScript renders the pages. Option C, a separate React single-page application over a Laravel JSON API, was the first selection and was superseded during Milestone 2 by CR-017.

Accountability is the first reason. Weak accountability for status changes is a core problem in the business need. D-002 makes the status history append-only, and D-008 writes the status change and its history row in one database transaction. That guarantee depends on both writes happening in one process against one database; option D would turn it into a distributed transaction.

Access control is the second reason. FR-013 lets staff combine search, filter and sort freely, so there is no single screen at which permissions can be checked. In option B every page visit is an ordinary authenticated request to Laravel, and ServiceRequestPolicy applies the same rule on every query path (D-012, ASR-002). Option C would need the same rules exposed through an API, with authentication carried across a network boundary using CORS and token handling.

Integrity is the third reason. A stale write is rejected by the optimistic version check in D-008 instead of silently overwriting another staff member’s change (R-008).

Cost rules out option D and weighs against option C. The cost constraint (CON-003) favours the fewest deployables, and option B runs as one web process, one queue worker and one PostgreSQL instance (D-013). A more distributed system is not automatically more advanced, and no requirement justifies the extra complexity.

The trade-off accepted with option B is coupling: the React pages and the Laravel application are released together, and page props are an internal contract rather than a reusable API. No requirement in the approved scope needs a second client, so this is accepted and tracked as R-016.

## 13.1.4 Physical deployment

The components in 13.1.1 are logical boundaries in the source tree, not separate processes. CivicConnect runs as three physical units:

Laravel web process: runs all the logical components in 13.1.1, handles every page visit and returns Inertia responses together with the React and TypeScript assets compiled by Vite.

Queue worker: runs php artisan queue:work from the same codebase and executes the queued NotifyRequesterOfStatusChange listener (D-011). Laravel’s scheduler, which runs the retention purge (FR-008), also runs from this codebase (13.7.3). PostgreSQL database: stores all application data and the job queue (database queue driver). It is a single point of failure, accepted at MVP under the cost constraint and mitigated by backups (13.7.5).

## 13.1.5 Architectural diagrams

shows the logical components inside the single Laravel deployable, the queue worker and scheduler that share its codebase, and the external mail provider.

# 13.2 Data and persistence baseline

## Intro

This section is the design-level explanation, and identifies the core data entities CivicConnect needs at this stage, sets out the initial data model, and commits the persistence approach that keeps a status change and its audit entry consistent. The full decision record is D-008 in Section 9.

## 13.2.1 Core data entities

| Table | Purpose | Traces back to |
| --- | --- | --- |
| users | Account data for every user: name, email, password hash and one of three roles. | FR-010, NFR-001, NFR-002 |
| categories | Seeded, controlled list of request categories, including ‘Other’. | FR-005, D-001, D-010 |
| service_requests | The root entity: requester, category, location, area, description, current status, assignee and version. | FR-001, FR-006, FR-023, D-008 |
| request_status_transitions | Seeded list of legal old-status / new-status pairs. | FR-017, D-015 |
| request_status_history | Append-only record of every status change: request, previous and new status, who and when. | FR-014, FR-019, NFR-003, D-002 |
| request_assignments | Offers, acceptances and self-assignments, with who and when. | FR-015, FR-016 |
| request_comments | Staff comments and resolution notes, with author and time. | FR-014, FR-020 |
| jobs, failed_jobs, Cache, cache_locks, job_batches, sessions, migrations, password_reset_tokens | Laravel database queue tables for queued notifications. | D-011 |

## 13.2.2 ERD

Figure 13.2 shows the initial schema. Table ownership and lifecycle are in 13.2.3

## 13.2.3 Data Ownership and Lifecycle

| Table | Owning component | Written by |
| --- | --- | --- |
| users | Authentication | Account creation (OD-10) and profile updates. |
| categories | Category handling | Seeded by migration; changed only through a migration and a change record. |
| service_requests | Submission (create); StatusAudit (status); Assignment (assignee) | Created by the submission service. Status changed only by RequestStatusService (D-008, R-011). Category changed only by an audited staff reclassification. |
| request_status_transitions | StatusAudit | Seeded by migration (D-015). |
| request_status_history | StatusAudit | Inserted inside the D-008 transaction; never updated; purged 5 years after the request’s last update. |
| request_assignments | Assignment | Written on offer, accept, decline and self-assignment. |
| request_comments | StatusAudit | Written when staff add a comment or resolution note. |
| jobs, failed_jobs | Notification | Written by the framework when the listener is queued or fails. |

## 13.2.4 Persistence model choice

The database that will be used is a relational model in PostgreSQL. The evidence for this decision is as follows:

| Factor | Evidence | Implication |
| --- | --- | --- |
| Structure | Users, categories, requests, assignments, comments and status history are separate entities linked by foreign keys, with one-to-many relationships from each request (13.2.1). | A relational model represents these relationships directly. A document store would duplicate user and category data inside every request. |
| Integrity | Status values and legal transitions must be enforced (FR-017, D-015), and every history row must point to a real request and user (FR-019). | PostgreSQL CHECK constraints, foreign keys and a composite foreign key to request_status_transitions act as a backstop behind service-layer validation. |
| Consistency | A status change and its audit row must succeed or fail together (D-002, D-008), and concurrent edits must not overwrite each other (R-008). | ACID transactions (DB::transaction) plus a version column for optimistic concurrency. No eventual consistency is needed at MVP. |
| Access patterns | Staff and management search, filter, sort and paginate lists (FR-009, FR-013); overdue is derived from timestamps (FR-023). | Indexes on status, category_id, assigned_to and updated_at; pagination at 50 rows per page (NFR-004, ASR-001). |
| Sensitivity | Security and IT-support requests may contain personal or safety-related information (CON-005, FEC 6). | Authorisation is applied at the data-access layer (D-012); passwords are hashed (NFR-001); encryption at rest depends on the provider (OD-05). |
| Growth | Records are kept 5 years after the last update (FR-008) on a free tier with a storage cap (CON-003, ASR-006). | Rows are small text records. A 5-year volume estimate is checked against the provider’s cap before OD-01 closes (AS-003), and the purge job removes expired rows. |

## 13.2.5 SPOF, scalability and bottlenecks

The single PostgreSQL instance is a single point of failure. This is accepted at MVP under the cost constraint (CON-003) and mitigated by the provider's backup and recovery facilities (13.7.5).

Horizontal scaling is not required at this stage. CivicConnect serves a single organisation, load grows gradually rather than in spikes, the architecture is a single deployable (D-006), and additional instances would exceed the free-tier constraint. NFR-004 is a response-time target and is met through indexing and pagination (13.2.4), not additional servers. If growth erodes that target, vertical scaling is the first response. Horizontal scaling becomes necessary only if load exceeds what one server can handle, or if the NFR-005 availability target requires removing the single point of failure.

Three bottlenecks are expected. The first is the database connection limit: free-tier PostgreSQL caps concurrent connections (CON-003), and every page request, the queue worker and each D-008 transaction hold one, so transactions are kept short. The second is reporting load: FR-024 aggregates over request_status_history, the fastest-growing table, on the same instance that serves day-to-day work; on-demand reporting (D-003) and indexes limit this. The third is the retention purge (FR-008): deleting a large batch of expired rows at once can lock tables, so the purge runs off-peak in batches.

## 13.2.6 Milestone 3 Update: schema prototype and verification.

Before the Laravel migrations were written the schema was built into a local database in PostgreSQL as a prototype. This was for the purpose of verifying the integrity rules before being carried over to the migrations, avoiding the need to replace the migrations if issues are found.

Additional rules were added beyond what figure 13.2, the ERD, shows. This is done as the ERD would have been difficult to read if these additional rules were added to the ERD itself.

Furthermore, there were 53 database-level checks on the tables and their relationships. They were run on 10/10/2026 and all passed the checks. The results are traced back to the RTM in section 6.3. The tests were re-run on 11/10/2026 and 12/10/2026 to ensure the database on NEON works as well.

Test data has been created in the form of Laravel seeders and migrations, using completely fictional users to mitigate the damage if the database is breached. Passwords are hashed using bcrypt at a cost factor of 12.. Test data includes all categories specified in D-001. Each status types is also covered in the test data. This data will be used for local development and will be used for the NFR-004 timing checks as well.

# 13.3 Tech Stack Analysis

## 13.3.1 Common web bundles

| Bundle ID | Bundle | Frontend | Backend | Database | Source |
| --- | --- | --- | --- | --- | --- |
| B-001 | MERN / PERN | React (JS/TS) | Node + Express | MongoDB (MERN) / PostgreSQL (PERN) | (Express, 2026) |
| B-002 | Next.js full-stack | React via Next.js | Next.js route handlers / server actions (Node), usually Prisma | PostgreSQL | (Next.js, 2026) |
| B-003 | LAMP / LEMP | Server-rendered PHP views (Blade) + light JS | PHP on Apache or Nginx, typically Laravel | MySQL / MariaDB (PostgreSQL also supported) | (Laravel, 2026a) |
| B-004 | Laravel API + SPA | React or Vue SPA (TypeScript) | Laravel JSON API (PHP) | PostgreSQL or MySQL | (Laravel, 2026b) |
| B-005 | Django | Django templates, or React with Django REST Framework | Django (Python) | PostgreSQL | (Django Software Foundation, 2026) |
| B-006 | ASP.NET Core | Razor Pages, Blazor, or React | ASP.NET Core (C#) + Entity Framework | SQL Server (PostgreSQL supported) | (Microsoft, 2026) |
| B-007 | Spring Boot | Angular or React | Spring Boot (Java) + JPA/Hibernate | PostgreSQL or MySQL | (Spring, 2026) |
| B-008 | Rails | ERB views with Hotwire/Turbo, or React | Ruby on Rails | PostgreSQL | (Ruby on Rails, 2026) |
| B-009 | Laravel + Inertia | React + TypeScript via Inertia | Laravel (PHP) | PostgreSQL | (Inertia.js, 2026) (Laravel, 2026c) |

The bundles were selected from the most widely used web frameworks among developers (Statista, 2026)

PostgreSQL capabilities are taken from the PostgreSQL Global Development Group (2026).

## 13.3.2 Candidates not recommended

MERN was excluded before scoring because MongoDB is not a relational database, and the data design (D-008, D-015) depends on transactions, foreign keys and CHECK constraints. Its relational variant, PERN (PostgreSQL), was kept and scored as B-001

## 13.3.3 Weight matrix

Scale: 1 = poor fit or high risk, 2 = weak, 3 = adequate with effort, 4 = good, 5 = strong, with evidence. Weights total 100. Maximum weighted score 500.

| Criteria | Weighting | Options |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  | B-001 | B-002 | B-003 | B-004 | B-005 | B-006 | B-007 | B-008 | B-009 |
| Requirement & ASR fit | 15 | 4 | 3 | 5 | 5 | 5 | 5 | 5 | 5 | 5 |
| Team capability | 8 | 3 | 3 | 2 | 2 | 4 | 4 | 4 | 2 | 2 |
| Framework & surface learning | 12 | 2 | 3 | 3 | 2 | 3 | 3 | 1 | 2 | 3 |
| Dev environment availability | 10 | 5 | 5 | 4 | 4 | 4 | 5 | 5 | 3 | 4 |
| Security ecosystem | 12 | 3 | 3 | 5 | 4 | 5 | 5 | 5 | 5 | 5 |
| Maintainability | 10 | 4 | 3 | 4 | 4 | 4 | 4 | 4 | 4 | 4 |
| Testing & tooling | 10 | 4 | 3 | 5 | 4 | 4 | 4 | 4 | 5 | 5 |
| Deployment & ops | 10 | 4 | 2 | 5 | 3 | 4 | 3 | 3 | 4 | 5 |
| Cost | 5 | 4 | 4 | 5 | 4 | 5 | 3 | 3 | 5 | 5 |
| Lock-in | 4 | 4 | 2 | 3 | 5 | 3 | 3 | 5 | 3 | 4 |
| Fallback consequence | 4 | 4 | 2 | 3 | 4 | 3 | 3 | 2 | 3 | 4 |
| Weighted total (/500) |  | 366 | 307 | 416 | 369 | 412 | 402 | 382 | 384 | 424 |
| Percentage (%) |  | 73 | 61 | 83 | 74 | 82 | 80 | 76 | 77 | 85 |

## 13.3.4 Weight matrix for database

| Criteria | Weight | PostgreSQL | MySQL / MariaDB | SQL Server |
| --- | --- | --- | --- | --- |
| Integrity support: CHECK constraints, composite foreign keys, transactional DDL | 30 | 5 | 3 | 4 |
| Team capability | 20 | 5 | 4 | 2 |
| Managed free-tier availability | 20 | 4 | 4 | 2 |
| Migrations and tooling support in the chosen stack | 15 | 5 | 4 | 4 |
| Cost and lock-in | 15 | 5 | 5 | 3 |
| Weighted total (max 500) |  | 480 | 385 | 305 |
| Percentage |  | 96 | 77 | 61 |

## 13.3.5 Results of the matrices

B-009 (85%), B-003 (83%), B-005 (82%) and B-006 (80%) fall within five percentage points of one another. The matrix therefore narrows the field to four defensible candidates rather than producing a single winner and the final selection is recorded in D-007 together with the stated tiebreakers.

Sensitivity check: halving the two capability criteria to ten points combined and reallocating those ten points to requirement and ASR fit gives B-009 90%, B-003 88%, B-005 86% and B-006 84%. The order of the leading four is unchanged, so the result is not an artefact of the weight placed on learning curve. A second check moved the weight the other way. Raising the two capability criteria to 30 points combined (team capability 12, framework learning 18) and reducing requirement and ASR fit to 5 gives B-009 80.0%, B-005 79.2%, B-003 78.4% and B-006 77.2%. B-009 remains first, but its lead falls to 0.8 points, so the ranking is sensitive to how heavily the learning curve is weighted. This is why the tiebreakers in D-007 matter.

## 13.3.6 Selected versions and compatibility

Target versions for the selected stack. Each is confirmed against composer.lock and package.json when the project is created. Any change after the baseline goes through the change record.

| Component | Target version | Reason / compatibility |
| --- | --- | --- |
| PHP | 8.3 or later | Laravel 13 supports PHP 8.3 to 8.5. Availability on the BC Desktop still to be verified (R-014, AS-002). |
| Laravel framework | 13.x | Current major release (March 2026): bug fixes until Q3 2027 and security fixes until Q1 2028, which covers the project. Laravel 12 bug fixes ended in August 2026. |
| Inertia (inertiajs/inertia-laravel, @inertiajs/react) | 3.x (confirmed from composer.lock at the start of M3) | Inertia v3 was released in March 2026. v2 bug fixes ended on 26 September 2026 (security fixes until 26 March 2027), so v3 is preferred for a new project. |
| React | 19.x (confirmed from package.json at the start of M3) | Rendered through the Inertia React adapter. |
| TypeScript | 5.x (confirmed from package.json at the start of M3) | Used by the official React starter kit. |
| Node.js | 20 LTS or later (confirmed against Vite’s minimum at the start of M3) | Needed for npm and the Vite build. |
| PostgreSQL | Version 18, both locally and on NEON. | The local Docker image must match the provider’s version (environment parity, Master Brief section 17). |
| Composer | 2.x | PHP dependency manager. |

# 13.4 Design Decisions

The two Assignment 2 design problems as final, defended Milestone 2 decisions. The full ADR entries are D-009 and D-010 in Section 9. This subsection is the design-level explanation with diagrams and code links.

## 13.4.1 Design Problem 1: Status-Change Side Effects

### Problem

A status change on a request is not a single-field update. FR-016 and FR-019 require an audit entry recording who made the change and when, and FR-007 requires the requester to see the update reflected on their side. Writing all of this directly inside the method that changes the status collects several unrelated reasons to change and becomes harder to extend, for example if an SLA-overdue escalation reaction is added at a later milestone.

### Assignment 2 Alternatives

Assignment 2 Task 1 compared a direct sequential-call approach against the Observer pattern and a full domain-event/pub-sub dispatcher, and recommended a uniform Observer applied at the ServiceRequest entity. A full dispatcher was set aside there as more infrastructure than a single event-raising entity needed.

### Final Decision (adapts the Assignment 2 recommendation)

Once Laravel was confirmed as the stack, its built-in event/listener mechanism removed the infrastructure cost that ruled out a dispatcher in the Assignment 2 research, but Assignment 2 Task 2's transaction requirement meant a uniform Observer would not work: an after-commit reaction cannot also be the audit write. The reactions were split: the audit history write happens synchronously inside RequestStatusService::transition(), inside the same database transaction as the status update (D-008). Every other reaction, currently the requester notification, is a queued listener (NotifyRequesterOfStatusChange) on the RequestStatusChanged event, dispatched only once that transaction has committed. RequestStatusChanged implements ShouldDispatchAfterCommit, so Laravel dispatches it only after the D-008 transaction commits; if the transaction rolls back, the event is never dispatched (Laravel, 2026c).

### Trade-off

The status-change reaction logic is no longer one uniform mechanism. A misconfigured listener still silently skips its reaction, the same risk a plain Observer would carry.

### Class / Flow Diagram

Figure: synchronous audit write inside the D-008 transaction, asynchronous notification only after commit.

### Planned implementation (Milestone 3)

These files do not exist yet. Construction begins in Milestone 3 (D-014). Paths will be replaced with repository links when they are created.

| Service | app/Services/RequestStatusService.php - transition() |
| --- | --- |
| Event | app/Events/RequestStatusChanged.php |
| Listener | app/Listeners/NotifyRequesterOfStatusChange.php (implements ShouldQueue) |
| Notification | app/Notifications/RequestStatusChangedMail.php |
| Test | tests/Feature/StatusTransitionTest.php |

## 13.4.2 Design Problem 2: Category-Specific Request Handling

### Problem

Decision D-001 fixed the category vocabulary itself, but not how category-specific validation and routing behaviour is implemented. Writing that behaviour as one long conditional inside the request-handling code means every new category requires editing and retesting that same method.

### Assignment 2 Alternatives

Assignment 2 Task 1 compared the Strategy pattern against Factory Method and a configuration-only lookup. The configuration-only approach was set aside because CivicConnect's categories differ in behaviour, not only in the fields they require. Factory Method was set aside because the categories differ in behaviour, not in data shape; a subclass per category would force a class hierarchy onto the persisted request and complicate the data model (Assignment 2, Task 1).

### Final Decision

The Strategy pattern is adopted as recommended. Each category implements a shared CategoryHandler interface (rules(), defaultAssignee()). CategoryRegistry, bound in AppServiceProvider, resolves the handler for a given category code. An unrecognised code falls back to OtherHandler. StoreServiceRequest merges the resolved handler's rules into its own FormRequest validation.

### Trade-off

Requires a small registry/lookup mechanism. If the category list stays very small with simple, near-identical rules, this is more structure than the problem needs.

### Class Diagram

Figure: CategoryRegistry resolves a CategoryHandler per category code; OtherHandler is the fallback.

### Planned implementation (Milestone 3)

These files do not exist yet. Construction begins in Milestone 3 (D-014). Paths will be replaced with repository links when they are created.

| Interface | app/Domain/Categories/CategoryHandler.php |
| --- | --- |
| Registry | app/Domain/Categories/CategoryRegistry.php |
| Handlers | app/Domain/Categories/Handlers/ (FacilityFault, DamagedEquipment, ItSupport, SecurityConcern, Maintenance, LostProperty, Other) |
| Binding | app/Providers/AppServiceProvider.php |
| Test | tests/Feature/CategoryHandlingTest.php |

# 13.5 UI & Information Architecture

The role-based site map, low-fidelity wireframes for the six screens in scope for Milestone 2, and the usability and accessibility rationale behind them (NFR-007, NFR-008).

## 13.5.1 Role Sitemap

Navigation is organised by role rather than by feature. Auth/Login is the single entry point for all three roles.

Which pages a logged-in user can reach is read from users.role, not chosen at login. Pages are React components in resources/js/Pages, rendered through Inertia. Laravel route middleware limits each route to the roles that use it, as a navigation convenience; the actual access control is ServiceRequestPolicy on the server (ASR-002).

Every page is reachable from the role landing page in at most two clicks, satisfying the three-click rule in NFR-007.

Figure: role sitemap - Inertia pages in resources/js/Pages.

Every screen is reachable from LoginPage in at most two clicks, satisfying the three-click rule in NFR-007. Route-level role guards are a usability convenience only; the actual access control is enforced server-side by ServiceRequestPolicy (ASR-002).

## 13.5.2 Wireframes

Low-fidelity: they fix what information and controls each screen needs, not final visual design.

Figure: low-fidelity wireframes - Requests/New, Requests/Index (requester and staff views), Requests/Show, Management/Dashboard and Auth/Login.

## 13.5.3 Usability and Accessibility Rationale

| Requirement | How the screens satisfy it |
| --- | --- |
| NFR-007 (3 clicks from main screen) | Every page is at most 2 clicks from the role landing page reached after Auth/Login. Requests/New and Requests/Index are 1 click from the requester landing page; Requests/Show is 1 click from Requests/Index. |
| NFR-008 (validation failures produce actionable messages) | When validation fails, Laravel redirects back to Requests/New with an error next to each field and the submitted values preserved. If the version is stale, Requests/Show reloads with the message “This request changed since you opened it. Please review and try again.” |
| FR-004 (submission feedback) | Submitting Requests/New always ends in either a confirmation on the created request or field-level errors; there is no silent failure state. |
| FR-012 (views provide relevant information) | Requests/Index shows the category, status, time submitted and assignee in each row. |

Formal accessibility testing is not scoped to Milestone 2; these wireframes fix the information architecture the accessibility work at Milestone 3 will build on.

# 13.6 Interfaces and Integration

Because D-006 selects an Inertia presentation layer, CivicConnect exposes no public API at Milestone 2. The interfaces described below are the boundaries that do exist, documented at the level currently established. Where an interaction is not yet established it is recorded as a forward engineering consideration rather than specified speculatively

## 13.6.1 Interface inventory

|  | Boundary | Type | Crosses a network boundary | Decision reference |
| --- | --- | --- | --- | --- |
| 1 | Browser to application | Inertia page visit over HTTPS, authenticated by session cookie | Yes, client to server | D-006, D-012 |
| 2 | Web process to queue worker | Job row written to the database queue and picked up by the worker | No, same codebase and same database | D-011 |
| 3 | Application to PostgreSQL | Database connection from the web process and the worker | Yes, to the managed database instance | D-007, D-008 |
| 4 | Application to mail provider | SMTP or provider API call made by the queued listener | Yes, external service | D-011, D-013 |

The only internal boundary the team introduced by choice is number 2, and it exists because D-011 requires a notification failure to be isolated from the status-change transaction. Boundaries 1, 3 and 4 are unavoidable for a browser-based application with a managed database and email delivery.

## 13.6.2 Page contracts

Inertia page visits replace the endpoint table an API-based design would have. Each route names the page component it renders, the props it sends, the input it accepts and how it responds. These props are an internal contract between a controller and its page component; they are not a published API.

| Route | Method | Page component | Props sent to the page | Input accepted | Responses | Requirements |
| --- | --- | --- | --- | --- | --- | --- |
| /login | POST | Auth/Login | none | email, password | Redirect to the role landing page; validation errors returned to the form | FR-010 |
| /logout | POST | - | none | none | Redirect to the login page | FR-010 |
| /requests/create | GET | Requests/New | Active categories, required fields for the selected category | none | Page | FR-005, D-010 |
| /requests | POST | - | - | category, location, area, description, category-specific fields | Redirect to the created request with a confirmation; field-level errors on failure | FR-001, FR-003, FR-004 |
| /requests | GET | Requests/Index | Paginated requests scoped to the user’s role, available filters, current sort | search, status, category, sort, page | Page | FR-002, FR-009, FR-012, FR-013 |
| /requests/{id} | GET | Requests/Show | Request, status history, comments, assignment state, allowed next statuses, current version | none | Page; 403 when the policy denies access | FR-006, FR-014 |
| /requests/{id}/status | PATCH | - | - | to_status, version | Redirect back with updated props; if the version is stale, redirect back with an error message; 403 when the user is not the assignee | FR-017, FR-018, FR-019 |
| /requests/{id}/assignments | POST | - | - | assignee_id, or self-assignment | Redirect with updated props; 403 when not authorised | FR-015, FR-016 |
| /assignments/{id} | PATCH | - | - | accept or decline | Redirect with updated props | FR-015 |
| /requests/{id}/comments | POST | - | - | body, is_resolution | Redirect with updated props | FR-020 |
| /reports/summary | GET | Management/Dashboard | Counts by status and category, overdue list, average time to resolution | date range | Page; 403 for any non-management role | FR-022, FR-023, FR-024 |

## 13.6.3 Failure behaviour

| Condition | Response | Requirement |
| --- | --- | --- |
| Input fails validation | Field-level messages returned to the originating form, with the submitted values preserved | FR-003, FR-004, NFR-008 |
| Policy denies the action | 403 with a generic message; the attempt is logged | FR-011, FR-018, NFR-002 |
| Version supplied is stale | Redirect back to Requests/Show with the message “This request changed since you opened it” and the current state reloaded | R-008, D-008 |
| Legal transition not found | Validation failure naming the allowed next statuses | FR-017, D-015 |
| Unexpected server error | Generic error page with no internal detail exposed | NFR-008 |

## 13.6.4 Internal event contract

RequestStatusChanged is the one internal payload that behaves like a contract, because a listener consumes it rather than sharing the caller’s memory of the request.

| Field | Purpose |
| --- | --- |
| request_id and reference number | Identifies which request the notification concerns |
| from_status, to_status | Describes the transition that occurred |
| actor_id | The staff member who made the change, for the message and for traceability |
| occurred_at | The timestamp recorded in the history row |
| requester contact address | Where the notification is delivered |

The event deliberately does not carry the full request entity, which follows the Assignment 2 Task 3 analysis of what information an interaction actually needs. Listeners are queued and retried on failure with a backoff; a permanently failed job is recorded in the failed jobs table and does not affect the committed status change.

## 13.6.5 External interface: mail provider

The queued listener is the only component that calls an external service. Credentials and the provider endpoint are supplied as environment variables and are never committed (section 13.7.2). The mail provider is Resend (D-019), called over HTTPS through Laravel's Resend driver, with the key held in environment variables. On staging, mail is sent synchronously (D-018), so a delivery failure must be caught and logged and must not undo the saved status change (D-011).

## 13.6.6 Change and versioning

Page props are internal: a controller and its page component change together in a single pull request, so no interface versioning scheme is required at this stage. If a JSON API is added later for a non-browser client, it becomes a published contract and requires versioning, deprecation handling and its own authentication decision. That possibility is recorded as an open decision in section 13.8 and as a trade-off in D-006 and R-016.

## 13.6.7 Interactions not yet established

The following interactions are recorded here rather than specified, because no requirement currently establishes them: third-party or partner integration; an export interface for reporting beyond the on-demand view in D-003; and any inbound channel from email, SMS or WhatsApp, which section 3.2 places out of scope. Each would require its own interface decision before implementation.

# 13.7 Deployment & Environments

The environment strategy for the selected stack (Laravel with Inertia serving React and TypeScript, and PostgreSQL) and the deployment risks it interacts with. The hosting provider for the application will be Render(D-018), but the database host has been decided (D-016).

## 13.7.1 Environment Structure

| Environment | Composition | Purpose |
| --- | --- | --- |
| Development | Local host running PostgreSQL for testing, switching to NEON for staging and production; Laravel served by php artisan serve (or a container); the Vite dev server for React assets; a local queue worker (php artisan queue:work). | Local development and manual testing with the same database engine and queue driver as production. |
| Test (CI) | GitHub Actions workflow (.github/workflows/tests.yml) with a PostgreSQL service container: composer install, npm ci, npm run build, php artisan migrate and php artisan test. | Every pull request is built and tested against real PostgreSQL before merge. |
| Staging / Production | One Laravel deployable serving Inertia pages and the compiled assets, one queue worker process, the scheduler, and a managed PostgreSQL instance on a free tier. Staging and production use separate databases. Provider for the application will be hosted on Render (D-013, OD-01, D-017), and the database host is NEON (D-016). | Demonstration, then real deployment. |

## 13.7.2 Configuration and Secrets

All environment-specific values are read from environment variables and never hard-coded: APP_KEY, APP_ENV, APP_URL, DB_CONNECTION, DB_HOST, DB_PORT, DB_DATABASE, DB_USERNAME, DB_PASSWORD, MAIL_MAILER, RESEND_KEY, MAIL_FROM_ADDRESS, MAIL_DEMO_TO and the mail provider credentials, SESSION_DRIVER, SESSION_SECURE_COOKIE and QUEUE_CONNECTION=database.

Render’s free tier, selected in D-018, runs no background processes, so AS-001 is not met. Staging therefore uses two replacements:

Notifications: QUEUE_CONNECTION=sync. The listener stays queued in the code but runs straight after the status change has been committed, sending through Resend’s HTTPS API (D-019). Because the status change is already saved, a mail failure is caught and logged and does not undo it (D-011). The cost is that the request waits while the email is sent, and there is no automatic retry.

Retention purge: a scheduled GitHub Actions workflow runs php artisan model:prune against the Neon database at 00:00 UTC (02:00 SAST), using connection details stored as encrypted GitHub secrets. It does not depend on the Render app being awake. (Planned; set up with the staging deployment.)

Moving to a host with background processes (Render’s paid tier, or option (b) in D-018) only requires QUEUE_CONNECTION=database and a worker process. The code does not change. This is tracked as R-009.

## 13.7.3 Queue worker and scheduler

D-011 makes NotifyRequesterOfStatusChange a queued listener. On a host that runs background processes, a queue worker (php artisan queue:work) delivers it after the response, and Laravel’s scheduler runs the retention purge (FR-008) daily at 02:00 (routes/console.php).

The retention purge (FR-008) runs from Laravel’s scheduler, so the host must also support either a cron entry running php artisan schedule:run every minute or a persistent php artisan schedule:work process.

Both are covered by Risk R-009 and assumption AS-001: a host without background processes would accept notifications that are never sent. Fallback: run queue:work --stop-when-empty from the scheduler, accepting delayed delivery.

## 13.7.4 Free-Tier Limits

Two limits interact directly with this work and are tracked as Risk R-013: a free-tier PostgreSQL instance that pauses when idle would make the demo unreliable, and the storage cap (R-002) interacts with the 5-year retention period on service_requests, request_status_history and request_comments. Mitigation: record the chosen host's actual limits once D-013 is finalised, seed a small, realistic dataset for the demo, and warm up the database connection before presenting.

Milestone 3 adheres to the limits by making use of NEON’s free plan. This allows for a free account capable of storing 1 GB of data per project, Meaning it can take an estimated 250,000 requests, as 310 test requests has taken up an estimated 1.08 MB. It provides 100 compute-unit hours and the suspension of the database when idle after 5 minutes (NEON, 2026). London was chosen to host the database as there was no option for it to be hosted in the African region.

Furthermore, the application will be hosted on Render. It also adheres to the limits as it is a free-tier service. It does however have limits of its own, such as the 15 minutes before sleeping, about a minute before it wakes up 750 hours of usage a month and 512MB of RAM. It also blocks SMTP. Tis is resolved by using Resend, which has its own limits of 100 emails a day, and only one recipient without a domain.

## 13.7.5 Backup and Recovery

NFR-006 requires data to be recoverable within 48 hours. Free tiers do not always include automatic backups (Supabase’s free plan, for example, does not) (supabase, 2026), so the baseline is a scheduled pg_dump of the database, run daily and stored outside the database host, with a restore rehearsed in Milestone 3. If the chosen provider includes daily backups or point-in-time recovery, that is used as an additional layer. A single PostgreSQL instance is accepted as a single point of failure at MVP under the cost constraint.

Milestone 3 partly adheres to the need of  backup and recovery as NEON’s free plan keeps a 6 hour change history. However, the documentation does not make it clear if the free tier plan allows for a point-in-time restore. The recovery baseline should still therefore remain the pg_dump for NFR-006.

# 13.8 Open and Deferred Decisions

Milestone 2 section 6 requires open decisions and deferred concerns to be identified separately from the approved baseline. None of the items below blocks the Architecture, Technology and Initial Design Baseline. Each is open because the evidence needed to decide it does not yet exist, and each names that evidence, an owner and the point at which it must be closed.

| ID | Open decision | Why it is still open | Evidence still needed | Owner | Decide by | Related records | Milsetone 3 status |
| --- | --- | --- | --- | --- | --- | --- | --- |
| OD-01 | Hosting provider | D-013 fixes the topology but not the provider | Background-worker support, backup and recovery facility, idle-pause behaviour, storage cap and pricing beyond the free tier | Michael | Before Milestone 3 staging deployment | D-013, R-002, R-009, R-013, FEC 4 | Closed. Database decided by D-016, and application decided by D-018 |
| OD-02 | Email delivery provider | Depends on the host and on free-tier send limits | Daily and monthly send allowances, sender-domain verification requirements, log retention | Jared | With OD-01 | D-011, R-009, section 13.7.4 | Closed by D-019 |
| OD-03 | Staff sub-roles by department | No stakeholder requirement for department-scoped visibility has appeared | Whether staff need to see only their department’s requests | Jared | Milestone 3, if a need appears | FEC 1, D-012, CR-009 |  |
| OD-04 | Depth of audit history exposed to staff | Retention is decided; how much history each role sees is not | Management input on whether staff need full history or only the current state | Xander | Milestone 3 | FEC 3, CR-012, FR-014 |  |
| OD-05 | Encryption at rest for sensitive categories | Depends on what the chosen provider offers and at what cost | Provider encryption options, key handling, cost impact | Xander | With OD-01 | FEC 6, D-012, ASR-002 |  |
| OD-06 | Static analysis as a blocking quality gate | Adopted as a warning first, following the Assignment 2 Task 4 recommendation | One clean run against real application code | Michael | Milestone 3 | Section 10.3, NFR-009 |  |
| OD-07 | Verification method for NFR-004 | The target is measurable but the measurement method is not chosen | A seeded data volume representative of five years and a repeatable timing approach | Michael | Milestone 3 test strategy | NFR-004, ASR-001 |  |
| OD-08 | Accessibility testing scope | Section 13.5.3 fixes the information architecture only | Which accessibility checks are feasible within the Milestone 3 window | Xander | Milestone 3 | NFR-007, NFR-008 |  |
| OD-09 | Whether a JSON API is added alongside Inertia | No second client exists and none is in scope | A stakeholder need for a non-browser client | Jared | Milestone 3 | D-006, R-016 |  |
| OD-10 | Account creation | No requirement defines how requesters and staff get accounts | Whether requesters self-register (starter-kit registration) and whether staff and management accounts are created by Management | Jared | Before the Milestone 3 authentication slice | FR-010, D-012, 13.2.3 |  |

Deliberately deferred rather than open:

construction itself is deferred to Milestone 3 under D-014, with the consequences recorded in R-015 and Forward Engineering Consideration 7. That is a decision with a date, not an unresolved question, which is why it appears in Section 9 rather than in this table.

14. Milestone 3: construction, quality and release readiness

## 14.1 Overview

The release candidate [insert release version] is one Laravel 13 + Inertia + React application on PostgreSQL. Built:

- registration and login with three roles.

- request submission with validation and a reference number.

- role-scoped request list with search, filters and 50 rows per page.

- detail page with history and comments.

- staff Take.

- management dashboard with status, category and overdue counts.

- 5-year retention purge.

- mail through Resend.

- status changes (start work, resolve, close), offers and declines, status-change emails and category handlers.

## 14.2 M2 baseline conformance

| M2 decision | Implemented | Evidence | Status |
| --- | --- | --- | --- |
| D-006/D-007 Inertia monolith, Laravel + React + PostgreSQL | As planned (Laravel 13, React 19, PostgreSQL 18) | routes/web.php, composer.json | Conforms |
| D-012 Session auth, policies | Role column, ServiceRequestPolicy, scopeVisibleTo() | RequestVisibilityTest | Conforms |
| D-015 Seeded transitions | Transition table, composite foreign key | Schema checks, TakeRequestTest | Conforms |
| D-008 Status service with version check | RequestStatusService; StaleRequestException on a version mismatch; Take uses a conditional update | RequestAssignmentController | Changed (CC-3) |
| D-009/D-011 Event + queued mail | RequestStatusChanged event, NotifyRequesterOfStatusChange listener, sent through Resend | config/mail.php | Conforms (runs synchronously on Render, D-018) |
| D-013 Deployment | Neon (D-016), Render (D-018), no worker | Section 9 | Changed (CC-1) |
| CR-012 Retention purge | Prunable, daily at 02:00 | ServiceRequest.php, routes/console.php | Conforms |
| D-010 Category handling | CategoryHandler, CategoryRegistry, 7 category handlers | CategoryHandlingTest | Conforms |

## 14.3 Controlled changes

| M2 decision | Implemented | Evidence | Status | Consequence |
| --- | --- | --- | --- | --- |
| CC-1 (D-018, CR-029) | Hosting deferred to M4 (D-017) | M3 postponed, same final deadline | Render free tier | No worker: synchronous mail, purge through GitHub Actions |
| CC-2 (D-019, CR-030) | Queued email, provider open (OD-02) | Render free tier blocks SMTP ports | Resend over HTTPS, demo inbox redirect | Emails reach one inbox; no retry |
| CC-3 (D-008) | Version check in RequestStatusService | [Jared: reason] | Take updates only open, unassigned rows and increments version | Double Take impossible; other transitions use the version check in RequestStatusService. |

## 14.4 Construction and configuration

Personal branches merge into Development through pull requests (#3 to #23), then into main which is protected (shown as a protected branch on GitHub). The team rule is two approvals per pull request ([https://github.com/Destroyer1819/SEN381_Project/rules/23877310?ref=refs%2Fheads%2Fmain]10.2, NFR-009).

Review evidence: Most reviewing happened as team discussions before pull requests were opened, causing the pull requests themselves to carry few review comments.

Secrets stay in .env (git-ignored), Render environment variables and GitHub secrets; .env.example lists the keys empty; tests use .env.testing with SQLite. Neon has separate staging and production branches, and production is never seeded.

Staging is hosted on Render's free tier (D-018), built from the Dockerfile and connected to the Neon staging branch, with Resend mail redirected to MAIL_DEMO_TO. Differences from production: local web server, Neon free-tier suspension, one demo inbox and seeded test accounts.differences from production are free-tier sleep, synchronous mail, one demo inbox and seeded accounts. Rollback: redeploy the previous tag and migrations are additive.

## 14.5 CI and automated verification

The Tests workflow runs on every pull request and on pushes to main and Development. dependency install from lockfiles, Pest (php artisan test), TypeScript type-check, ESLint and Vitest. Any failure marks the pull request as failing. Main is protected by the “Main Protection” ruleset (pull request and 2 approvals required), but a passing CI run is not yet a required status check, so the team rule is to merge only after a green run, as with PR #18 and PR #23.

Passing run: run #17, https://github.com/Destroyer1819/SEN381_Project/actions/runs/38868569090.

Failed runs that blocked a merge: runs #7 and #8 on PR #18 failed at the frontend install step (pnpm lockfile mismatch, DF-08) and the fix passed in run #9 before merging. run #15 on PR #23 failed the type-check (DF-09) and passed in run #16 after 1fb7142.

Static and security gates: Pint checks PHP code style, composer audit and pnpm audit (high and above) check dependencies for known vulnerabilities.

Gaps: no secrets scan, Playwright and PostgreSQL not in CI, no coverage collected.

## 14.6 Quality strategy applied

| Risk | Stronger verification |
| --- | --- |
| Data shown to the wrong role (ASR-002, FR-010, FR-011) | Decision-table tests over role x assignment state; 403 tests; TC-E2E-02 |
| Invalid or lost submissions (ASR-003, FR-001, FR-003, FR-004) | Equivalence partitions and boundary values, server and client |
| Two staff take one request (R-008, FR-015) | Conditional update and an "already assigned" test |
| Wrong dashboard figures (FR-023, FR-024) | Integration test with controlled data |
| Status and history integrity (FR-017, FR-019) | 53 PostgreSQL schema checks, also on Neon |

## 14.7 Black-box, integration and system validation

Against the brief's minimums: 32 Vitest unit/component cases; black-box cases in SubmitRequestTest and RequestVisibilityTest; Pest integration tests through HTTP, policy and database; 3 Playwright E2E tests. Techniques: equivalence partitioning, boundary values, decision table, state transition. Negative cases: guest redirects, 403 on Take, Comment and Dashboard, invalid input. Execution evidence for automated rows: the CI run above.

| ID | Basis | Technique / level | Input | Expected | Status |
| --- | --- | --- | --- | --- | --- |
| TE-01 | FR-003 | BVA / feature + unit | Description 9, 10, 2000, 2001 characters | 9 and 2001 rejected, 10 and 2000 accepted | Pass |
| TE-02 | FR-003, FR-004 | EP, negative | Empty form; unknown category | Field messages, nothing saved | Pass |
| TE-03 | FR-011 | Decision table / integration | 3 roles x 4 assignment states | Each role sees exactly its set; others 403 | Pass |
| TE-04 | FR-015, R-008 | State, negative / integration | Already assigned; non-staff tries Take | 403, assignment unchanged | Pass |
| TE-05 | FR-023 | Integration | 4 controlled requests, 1 older than 7 days | total 4, overdue 1 | Pass |
| TE-06 | Core journey | E2E (TC-E2E-01 to 03) | Seeded accounts | Submit to resolve; access blocked; dashboard filter | Pass (Render staging, 16/10/2026) |

## 14.8 Performance and reliability

Operation: the request list with search and filters (GET /requests), the most frequent staff and management operation. NFR-004 allows 1 s per 100 rows; a page holds 50 rows, so the target is at most 500 ms per page.

Test: e2e/perf.spec.js (Playwright) logs in as the management user and requests each scenario 20 times after one warm-up request. Environment: Windows, app served with php artisan serve, local PostgreSQL 18 database. Data: 5,000 generated requests (SEED_REQUESTS=5000) plus the scenario data.

| Scenario | Median | 95th percentile | Max | Errors |
| --- | --- | --- | --- | --- |
| No filters (page 1) | 83 ms | 120 ms | 182 ms | 0 / 20 |
| Status + category filter | 76 ms | 84 ms | 119 ms | 0 / 20 |
| Text search (“room”) | 84 ms | 90 ms | 193 ms | 0 / 20 |

## Result: every request was well under the 500 ms target, with no errors, so NFR-004 is met in this environment. This does not, however, include the latency added by the distance due to the NEON hosted database being hosted in London.

## 14.9 Defects and quality interpretation

## Ten defects were recorded (Section 16) and all are fixed. Most came from environment and tooling (Windows server start-up, pnpm versions, the type-check, clashing test data) or from test timing, rather than from business rules, and CI or the test suites caught them before they reached Development. The most serious, DF-04, could have shown requests to the wrong staff member; RequestVisibilityTest found it and now guards against it. The main remaining concern is untested behaviour rather than known defects: PostgreSQL-only constraints and row locks (including the lock that stops two simultaneous offer declines) are not exercised by the SQLite test run, and the status-change, offer and category-handler code was merged last, so it has the least time in use beyond its automated tests.

## 14.10 Release readiness

| Area | Result | Interpretation / action |
| --- | --- | --- |
| Build & CI | Pass | Install, Pint, composer and pnpm audits, Pest, type-check, ESLint and Vitest pass on the release candidate https://github.com/Destroyer1819/SEN381_Project/actions/runs/38868569090 |
| Automated regression | Pass | Visibility, submission, Take, comments, dashboard protected. |
| API / integration | Pass | Built features work through HTTP, policy and database (SQLite) |
| System / E2E | Pass | TC-E2E-01 to 03 passed against Render staging (14.4); 3 passed in 42.6 seconds total. |
| Static / security | tsc, ESLint, Pint and audits pass | Secrets scan not configured. |
| Performance | Median 76 to 84 ms, max 193 ms, 0 errors | Meets NFR-004 (≤ 500 ms per page) locally; not tested at scale or on Neon |
| Known defects | 0 open | Section 16 |
| Acceptance | 24 of 24 FRs implemented | 2 have automated tests; FR-009 (50 per page) and FR-012 (list columns) were checked by hand (RTM 6.3) |

Classification: CONDITIONALLY READY. All required checks pass and the core journey works end to end. The conditions are non-blocking: status emails reach one demo inbox, PostgreSQL-only behaviour is checked by schema tests rather than in CI, and the offer rule (D-020) awaits final team confirmation.

| Residual risk | Why it remains | Mitigation / next action |
| --- | --- | --- |
| PostgreSQL constraints and locks untested automatically | CI runs on SQLite | 53 schema checks on Neon; add PostgreSQL to CI |
| Free-tier cold starts and limits | Render and Neon sleep when idle | Warm up before the demo; paid tier before real use |
| Emails reach one inbox, no retry | Resend without a domain; synchronous sending | Verify a domain and restore a worker |
| Scale untested | Single-user local test | Add indexes; retest in a representative environment |

# 15. Technical Debt Register

| ID | Item | Consequence | Next action |
| --- | --- | --- | --- |
| TD-01 | Visibility rule in two places (scopeVisibleTo, policy) | Can drift and leak data | One shared rule |
| TD-02 | Transition table and status CHECK kept in step by hand | New status needs two edits | Add a consistency test |
| TD-03 | Tests run on SQLite | CHECKs and locks untested | PostgreSQL in CI |
| TD-04 | No index on status or updated_at (13.2.4 says there is) | Slower filters and purge | Add one migration |
| TD-05 | Synchronous mail, no worker (D-018) | Slower status changes, no retry | Worker host |
| TD-06 | Seeded accounts share one known password | Risky on public staging | SEED_PASSWORD |
| TD-07 | No notification list, password reset or timezone rule for dates (frontend) | Usability gaps | Next milestone |

# 16. Defect Register

| ID | Defect | Severity | Fix | Regression evidence | ID |
| --- | --- | --- | --- | --- | --- |
| DF-01 | artisan serve failed on Windows | Low | d404dbd | Manual | DF-01 |
| DF-02 | Frontend test failure | Low | 32e57b6 | Vitest | DF-02 |
| DF-03 | Home redirected to /settings/profile | Low | 1b1c449 | Manual | DF-03 |
| DF-04 | Visibility scope returned the wrong set | High | 3b62324 | RequestVisibilityTest | DF-04 |
| DF-05 | Schema-check test IDs clashed with seeded rows | Medium | IDs moved to 900001+ | 53/53 re-run | DF-05 |
| DF-06 | E2E used accounts the seeders don't create | Medium | 832b8ec | E2E login passes | DF-06 |
| DF-07 | E2E picked a category before the form loaded | Low | 832b8ec | TC-E2E-01 submit step | DF-07 |
| DF-08 | CI install failed: pnpm 12 ignored package.json overrides | Medium | 5752253, 3bf3e07 (CI runs #7, #8 failed; #9 passed) | CI install step | DF-08 |
| DF-09 | Unused UI components broke the type-check | Medium | 1fb7142 | CI run #15 failed, #16 passed | DF-09 |
| DF-10 | E2E-01 checked the status before the detail page had loaded, so other resolved requests could give a false result | Low | dbc08b7 | TC-E2E-01 final step | DF-10 |

# References

Copes, F., 2026. Every hosting provider's free tier, side by side. [Online] 
Available at: https://flaviocopes.com/hosting-free-tiers/
[Accessed 15 Oktober 2026].

Django Software Foundation, 2026. Django at a glance. [Online] 
Available at: https://docs.djangoproject.com/en/stable/intro/overview/
[Accessed 26 September 2026].

Express, 2026. Express - Node.js web application framework. [Online] 
Available at: https://expressjs.com
[Accessed 26 September 2026].

Inertia.js, 2026. How it works. [Online] 
Available at: https://inertiajs.com/how-it-works
[Accessed 26 September 2026].

ISO, 2023. ISO/IEC 25010:2023 Systems and software engineering - Systems and sofware Quality Requirements and Evaluation (SQuaRE) - Product Quality model, International Organisation for Standardization: Geneva.

Jeff, S., 2011. What Is A Good Task-Completion Rate?. [Online] 
Available at: https://measuringu.com/task-completion/
[Accessed 13 September 2026].

Laravel, 2026a. Blade Templates. [Online] 
Available at: https://laravel.com/docs/blade
[Accessed 26 September 2026a].

Laravel, 2026b. Laravel Sanctum. [Online] 
Available at: https://laravel.com/docs/sanctum
[Accessed 26 September 2026b].

Laravel, 2026c. Starter Kits. [Online] 
Available at: https://laravel.com/docs/starter-kits
[Accessed 26 September 2026c].

Meta, 2026. Pricing on the WhatsApp Business Platform. [Online] 
Available at: https://developers.facebook.com/documentation/business-messaging/whatsapp/pricing
[Accessed 13 September 2026].

Microsoft, 2026. Overview of ASP.NET Core. [Online] 
Available at: https://learn.microsoft.com/en-us/aspnet/core/introduction-to-aspnet-core
[Accessed 26 September 2026].

NEON, 2026. Neon pricing. [Online] 
Available at: https://neon.com/pricing
[Accessed 12 10 2026].

Next.js, 2026. Documentation. [Online] 
Available at: https://nextjs.org/docs
[Accessed 26 September 2026].

Nielsen, J., 1993. Response Times: The 3 Important Limits. [Online] 
Available at: https://www.nngroup.com/articles/response-times-3-important-limits/
[Accessed 13 September 2026].

POPIA, 2019. Section 14 Retention and restriction of records. [Online] 
Available at: https://popia.co.za/section-14-retention-and-restriction-of-records/
[Accessed 27 September 2026].

PostgreSQL Global Development Group, 2026. About PostgreSQL. [Online] 
Available at: https://www.postgresql.org/about/
[Accessed 26 September 2026].

Ruby on Rails, 2026. Getting Started with Rails. [Online] 
Available at: https://guides.rubyonrails.org/getting_started.html
[Accessed 26 September 2026].

Spring, 2026. Spring Boot. [Online] 
Available at: https://spring.io/projects/spring-boot
[Accessed 26 September 2026].

Statista, 2026. Most used web frameworks among developers worldwide as of 2025. [Online] 
Available at: https://www.statista.com/statistics/1124699/worldwide-developer-survey-most-used-frameworks-web/
[Accessed 26 September 2026].

supabase, 2026. https://supabase.com/pricing. [Online] 
Available at: https://supabase.com/pricing
[Accessed 13 September 2026].

Tovarys, J., 2022. Availability Table. [Online] 
Available at: https://betterstack.com/community/guides/incident-management/availability-table/
[Accessed 13 September 2026].

Translated, 2025. Software Localization Cost: Application Translation Pricing & Budget Guide. [Online] 
Available at: https://translated.com/resources/software-localization-cost-application-translation-pricing-budget-guide
[Accessed 13 September 2026].

VerifyNow, 2025. https://www.verifynow.co.za/how-to-comply-with-rica-in-south-africa-your-comprehensive-guide. [Online] 
Available at: https://www.verifynow.co.za/how-to-comply-with-rica-in-south-africa-your-comprehensive-guide
[Accessed 13 September 2026].